## Issue Tracker (hidden)
Project | Date | Aging in Days | ID | Issue Description | Functional | Client Sign Off | Received | Status | Issue raised By | Expected Target Date | Invoice Number | Others | Qtr | Status as on 9th July 2021 | Column1 | Remarks | Action By | TR Details | Estimated Closure Date | Closed Date
COPT | 2024-04-08 | 0 | 20240804001 | With respect to users does not have PD Account number, other passes are being displayed in the "Duplicate Wharf Entry Pass" list. Please ensure to restricted the same | DuplicateWharfEntryPassList | Shivhar | 2024-04-08 | Closed | Viju |  |  |  |  | As per the discussion on 18/03/2021 since there is no escalation from functional department, the ticket is closed
COPT | 05.04.2024 | 0 | 20240504001 | Several of our customers have expressed concerns about not receiving SMS/Email alerts for OTP regarding forgotten passwords. | WharfEntryPass | Venkatasagar | 2024-04-05 | Closed | Viju
COPT | 15.03.2024 | 0 | 20241503001 | Noticed certain discrepancies in the "Vessel type" dfined in PortKonnect application. Hence collected the master data from NLP-M in excel format and shared to NIT Team to update the same in the POS application. | Generate Invoice/interim Invoice | Pramod | 2024-03-15 | Closed | Viju
COPT | 22.02.2024 | 0 | 20242202001 | We have encountered several instances in the past where CALINV API messages were not reflected on the NLP-M site. Needs facility to check logs etc to acess the Response from the remote server | PCS File Process | Pramod | 2024-02-22 | Closed | Viju | 2024-06-17 |  |  |  | As per the discussion on 18/03/2021 since there is no escalation from functional department, the ticket is closed
COPT | 07.02.2024 | 0 | 20240702001 | Discripancy in Gate-in Gate-out Report, where the gate-in and gate-out times overlaped with the previous gate-in and gate-out times of the same vehicle. | Gate Operations | Pramod | 2024-02-07 | Closed | viju
COPT | 31.01.2024 | 0 | 20243101001 | ACKMSG Message - <Message type> node value should be as below:- 6 - if CALINF received well 27 - if CALINF received as error status 1 - if CALINF is cancelled | PCS File Process | Pramod | 2024-01-31 | Closed | Viju
COPT | 31.01.2024 | 0 | 20243101002 | TPFREP Message - <SaCode> Node value should be the PD Account number of the Shipping Agent as like handled in CALINV & BERALT Message. | PCS File Process | Pramod | 2024-01-31 | Closed | Viju
COPT | 2024-02-01 | 539 | 20240102001 | Ticket#202401050000006 — Count of Messages | PCS File Process | Pramod | 2024-02-01 | Pending | Viju | 2024-06-17
COPT | 2024-01-29 | 0 | 20242901001 | SMS Template :- Requesting the modification of "Cochin Port Trust" to "Cochin Port Authority" in all the SMS messages. | WharfEntryPass | Venkatasagar | 2024-01-29 | Closed | Viju
COPT | 2023-11-02 | 630 | 20230211001 | Agent change request | Change of agent | Pramod | 2023-11-02 | Pending (completed) | Viju | 2024-06-10 | [5 empty] | Deployed in Staging ( Testing is going on)
COPT | 2023-10-17 | 0 | 20231710001 | Login Issue:- We are not able to access "Wharf Entry Pass" from Login Screen via Firefox browser (Version 118.0.2 (32-bit)). It is working fine with Chrome browser. | WharfEntryPass | Venkatasagar | 2023-10-17 | Closed | Viju
COPT | 26-09-2023 05-10-2023 | 0 | 20232609001 | VESPRO & CALINV Messages :- At the time when VCN (INCOK123090093) was allocated to the ship EMPRESS (IMO-8716899), its Vessel Profile categorized it as a "Cruise ship." However, we subsequently received an updated VESPRO from GOA Port, which reclassified it as a "Passenger Ship." This alteration had a direct impact on the allocated VCN, causing a shift in the ship's type from "Cruise ship" to "Passenger ship." Consequently, this adjustment affects our billing process, as it denies the customer eligibility for special rates designated for "Cruise ships" and necessitates additional administrative efforts, such as issuing Credit Notes to the customer. Hence, request that the necessary steps be taken to maintain the ship's type as it was at the time of VCN allotment until the final billing process associated with that VCN is completed. | PCS File Process | Venkatasagar | 26-09-2023 05-10-2023 | Closed | Viju
COPT | 21-08-2023 11-09-2023 18-09-2023 03-10-2023 05-10-2023 | 703 | 20232108001 | IGM Related Issues :- 1) Many of the IGM files are not get processed and throws erros at fileprocessing screen. 2) It has come to our attention that despite the IGM file being uploaded into the system , it remains inaccessible for mapping at CFS screen due to Primary key violation (according to Quixy Team, Same Container No appears in multiple line no and subline no in the IGM file. NLP-M Ticket Ref: Ticket#202401120000021). 3) Ensure to update all below variance of IGM files to the system Different values of <MessageId> tag and its meaning is given below: CHPOI03A - On submission of manifest (After allowing IGM No) CHPOI03B - 48 Hrs before the expected time of arrival CHPOI03C - After 1 Hr of grant of entry inward CHPOI03D- Amended IGM | PCSFileLog | Pramod | 2023-08-21 | Pending | Viju | 2024-06-13 | [5 empty] | in QA
COPT | 2023-09-26 | 0 | 20232609001 | Need to schedule Holiday --amendment | Administration | Venkatasagar | 2023-09-26 | Closed | Viju
COPT | 2024-04-16 | 0 | 20241604001 | Disc space in all servers-resolution | DB Server | DB team | 2024-04-16 | Closed | Viju | 24th Apr 24
COPT | 2024-04-16 | 0 | 20241604002 | Assessment of unused space all servers and move to the required servers | DB Server | DB team | 2024-04-16 | Closed | Viju | 29th Apr 24
COPT | 2024-04-01 | 0 | 20240401001 | change of vessel type for INCOK124030087 | Generate Invoice/interim Invoice | Shivhar | 2024-04-01 | Closed | Whatsapp
COPT | 2024-04-02 | 0 | 20240402001 | IGM for LPG/C. NANDA DEVI VOY. ND056 ETA Cochin MULT Berth on 30.03.2024 - 1300 Hrs AGW WP | Import General Minifest | Shivhar | 2024-04-02 | Closed | Nasar C H
COPT | 2024-04-02 | 0 | 20240402002 | igm quqntity missmatch for incok124030144 | Import General Minifest | Venkatasagar | 2024-04-02 | Closed | Whatsapp
COPT | 2024-04-05 | 0 | 20240405001 | ATA update for INCOK12440017 | Service Recordings | Shivhar | 2024-04-05 | Closed | Whatsapp
COPT | 2024-04-05 | 0 | 20240405002 | Draft has been updated for INCOK123110146 | VoyageRegistrations | Shivhar | 2024-04-05 | Closed | Whatsapp
COPT | 2024-04-10 | 0 | 20240410001 | screenshort wharf entry pass -1.doc | WharfEntryPass | Venkatasagar | 2024-04-10 | Closed | Viju Varghese
COPT | 2024-04-11 | 0 | 20240411001 | RE: IGTPL Data March 2024 | IGTPL Data Upload | Shivhar | 2024-04-11 | Closed | sajith
COPT | 2024-04-12 | 0 | 20240412001 | RE: Port Users Pass | Users information | Venkatasagar | 2024-04-12 | Closed | Biswajith MenonP
COPT | 2024-04-12 | 0 | 20240412002 | update Clod move for incok120050015 ship 23 | Generate Invoice/interim Invoice | Shivhar | 2024-04-12 | Closed | Whatsapp
COPT | 2024-04-15 | 0 | 20240415001 | RE: VISION-INCOK124040057- Change of Agent. | Generate Invoice/interim Invoice | Shivhar | 2024-04-15 | Closed | Lalmon NK
COPT | 2024-04-15 | 0 | 20240415002 | RE: Fresh water supply-SSL Gujarat | Supplementary Service request | Shivhar | 2024-04-15 | Closed | Lalmon NK
COPT | 2024-04-15 | 0 | 20240415003 | Correction of Towage Charges | Generate Invoice/interim Invoice | Shivhar | 2024-04-15 | Closed | Viju Varghese
COPT | 2024-04-15 | 0 | 20240415004 | Change for GRT | Generate Invoice/interim Invoice | Shivhar | 2024-04-15 | Closed | Dinesan MK
COPT | 2024-04-15 | 0 | 20240415005 | Port Users Pass | Users information | Venkatasagar | 2024-04-15 | Closed | Biswajith MenonP
COPT | 2024-04-15 | 0 | 20240415006 | Fresh water supply-SSL Gujarat | Supplementary Service request | Shivhar | 2024-04-15 | Closed | Lalmon NK
COPT | 2024-04-15 | 0 | 20240415007 | Pcs feil reposting error | PCS File Process | Venkatasagar | 2024-04-15 | Closed | Whatsapp
COPT | 2024-04-16 | 0 | 20240416001 | RE: Correction in shipping bill mapping list - reg | Shipping Bill | Shivhar | 2024-04-16 | Closed | Abi Mathew
COPT | 2024-04-16 | 0 | 20240416002 | Correction in shipping bill mapping list - reg | Shipping Bill | Shivhar | 2024-04-16 | Closed | Abi Mathew
COPT | 2024-04-16 | 0 | 20240416003 | Change the rate in the "Rate column" | Generate Invoice/interim Invoice | Shivhar | 2024-04-16 | Closed | Dinesan MK
COPT | 2024-04-16 | 0 | 20240416004 | changeberth NO. Q1 for vcn incok124040058 | Generate Invoice/interim Invoice | Shivhar | 2024-04-16 | Closed | Whatsapp
COPT | 2024-04-17 | 0 | 20240417001 | service recording error for incok124020036 Swaran Kalash | Service Recordings | Shivhar | 2024-04-17 | Closed | Whatsapp
COPT | 2024-04-18 | 0 | 20240418001 | RE: SWARNA KALASH INCOK124020036 error showing in service recording | Service Recordings | Shivhar | 2024-04-18 | Closed | Ebanazer NV | [8 empty] | DE1K901560
COPT | 2024-04-19 | 0 | 20240419001 | RE: INCOK124040099 VALIYAPANI - Error | Generate Invoice/interim Invoice | Shivhar | 2024-04-19 | Closed | Ebanazer NV
COPT | 2024-04-19 | 0 | 20240419002 | RE: Fresh water supply-Apinya Naree | Supplementary Service request | Shivhar | 2024-04-19 | Closed | Thomas Mathew
COPT | 2024-04-19 | 0 | 20240419003 | RE: IGM reposting error - reg. | PCS File Process | Venkatasagar | 2024-04-19 | Closed | Viju Varghese
COPT | 2024-04-19 | 0 | 20240419006 | Fresh water supply-Apinya Naree | Supplementary Service request | Shivhar | 2024-04-19 | Closed | Thomas Mathew
COPT | 2024-04-22 | 0 | 20240422001 | RE: Container Vessels Teu Capacity | Vessel Profile | Shivhar | 2024-04-22 | Closed | Biswajith MenonP
COPT | 2024-04-22 | 0 | 20240422002 | vcn 040097 Dawn Mannsarovar shiffiting pilot name repeated | Shipping Program | Shivhar | 2024-04-22 | Closed | Whatsapp
COPT | 2024-04-23 | 0 | 20240423001 | RE: Add new Pilots Name in PortKonnect - reg | ServiceRequests | Shivhar | 2024-04-23 | Closed | Ebanazer NV
COPT | 2024-04-23 | 0 | 20240423002 | RE: NANDA DEVI-INCOK124040023 | Generate Invoice/interim Invoice | Shivhar | 2024-04-23 | Closed | Lalmon NK
COPT | 2024-04-23 | 0 | 20240423003 | update vcn NO for BRGCP2400001 shun 1 | VoyageRegistrations | Venkatasagar | 2024-04-23 | Closed | Whatsapp
COPT | 2024-04-23 | 0 | 20240423004 | sailling requst verification error | ServiceRequests | Shivhar | 2024-04-23 | Closed | Whatsapp
COPT | 2024-04-24 | 0 | 20240424001 | RE: Correction in Draft Survey Records - reg. | VoyageRegistrations | Shivhar | 2024-04-24 | Closed | Abi Mathew
COPT | 2024-04-24 | 0 | 20240424002 | RE: Change GRT | Generate Invoice/interim Invoice | Shivhar | 2024-04-24 | Closed | Dinesan MK
COPT | 2024-04-24 | 0 | 20240424003 | RE: INCOK124040133 MSC ARCHIMIDIS - MAINLINE VESSEL | Generate Invoice/interim Invoice | Shivhar | 2024-04-24 | Closed | Ebanazer NV
COPT | 2024-04-24 | 0 | 20240424004 | RE: change of Agent. APINYA NAREE-INCOK124040104 | Generate Invoice/interim Invoice | Shivhar | 2024-04-24 | Closed | Lalmon NK
COPT | 2024-04-24 | 0 | 20240424005 | RE: Ticket#202403140000046 — Master data synchronization - "Vessel type" and "Port of Registry" | Vessel Profile | Venkatasagar | 2024-04-24 | Closed | Viju Varghese
COPT | 2024-04-24 | 0 | 20240424006 | Change GRT | Generate Invoice/interim Invoice | Shivhar | 2024-04-24 | Closed | Dinesan
COPT | 2024-04-24 | 0 | 20240424007 | INCOK124040133 MSC ARCHIMIDIS - MAINLINE VESSEL | Generate Invoice/interim Invoice | Shivhar | 2024-04-24 | Closed | Ebanazer
COPT | 2024-04-24 | 0 | 20240424008 | Financial Analysis report not working | Financial Analysis report | Dilshad | 2024-04-24 | Closed | Viju Varghese
COPT | 2024-04-30 | 0 | 20240430001 | RE: valid_to date - Extension | Import General Minifest | Venkatasagar | 2024-04-30 | Closed | Viju Varghese
COPT | 2024-04-30 | 0 | 20240430002 | Vcn 24040073 Swarna Pushp not showing in shipping program | Shipping Program | Venkatasagar | 2024-04-30 | Closed | Whatsapp
COPT | 2024-05-02 | 0 | 20240502001 | Sailing request not showing in shipping progarm screen-VCN040161 SERENADE OF THE SEAS | Shipping Program | Venkatasagar | 2024-05-02 | Closed | Whatsapp(RAJANI MAM)
COPT | 2024-05-02 | 0 | 20240502002 | BERTHING request not showing in shipping progarm screen-VCN040137 WAN HAI 515 | Shipping Program | Venkatasagar | 2024-05-02 | Closed | Whatsapp(RAJANI MAM)
COPT | 2024-05-02 | 0 | 20240502003 | User unable save the temporary gate pass (save button is disable) | Gate Operations | Shivhar | 2024-05-02 | Closed | Whatsapp -Biswajith
COPT | 2024-05-02 | 0 | 20240502004 | Issue on repost IGM | PCS File Process | Venkatasagar | 2024-05-02 | Closed | Naser- whatsapp
COPT | 2024-05-02 | 0 | 20240502005 | As per SOR composite package applicable for this vessel.Please note that this vessel built from Private Jetty Cochin and sailout as Foreign,So please remove the inward pilotage in this Estimation Invoice. | Generate Invoice/interim Invoice | Shivhar | 2024-05-02 | Closed | Mail-Ebanazer
COPT | 2024-05-02 | 0 | 20240502006 | while reposting the IGM for the following vessel through PCS Files Processing getting error message is in seen | PCS File Process | Venkatasagar | 2024-05-02 | Closed | Mail-Abi Mathew
COPT | 2024-05-02 | 0 | 20240502007 | Please update pull back end time for 22:45 |  | Shivhar | 2024-05-02 | Closed | Rajani
COPT | 2024-05-02 | 0 | 20240502008 | SERENADE OF THE SEAS-INCOK124040161 - Marine Invoice Incorrect | Generate Invoice/interim Invoice | Shivhar | 2024-05-02 | Closed | Mail-Ebanazer
COPT | 2024-05-03 | 0 | 20240503001 | INCOK124040156 CELESTE - total amount(315604.7 ),Please correct total amount. | Generate Invoice/interim Invoice | Shivhar | 2024-05-03 | Closed | Mail-Ebanazer
COPT | 2024-05-03 | 0 | 20240503002 | Please update vessel type Cruise Ship instead of Passenger ship | Estimation Invoice | Shivhar | 2024-05-03 | Closed | Mail-Ebanazer
COPT | 2024-05-03 | 0 | 20240503003 | Please check berth name Q8 to DG | Application for Berthing | Shivhar | 2024-05-03 | Closed | Rajani
COPT | 2024-05-03 | 0 | 20240503004 | Please remove repeated pilot name | Shipping Programme | Shivhar | 2024-05-03 | Closed | Rajani
COPT | 2024-05-06 | 0 | 20240506001 | SAN PRIDE - INCOK122070087 - Marine Invoice Error. | Generate Invoice/interim Invoice | Shivhar | 2024-05-06 | Closed | Mail-Ebanazer
COPT | 2024-05-06 | 0 | 20240506002 | Marine Invoice Pending - SM KAVERI-INCOK124050022 | Estimation Invoice | Shivhar | 2024-05-06 | Closed | Ebanazer NV
COPT | 2024-05-06 | 0 | 20240506003 | IGTPL Data April 2024 | IGPTL Upload | Shivhar | 2024-05-06 | Closed | sajith
COPT | 2024-05-07 | 0 | 20240507001 | The "Forgot Password" option is currently not functioning properly | Forgot Password | Shivhar | 2024-05-07 | Closed | Mail-Viju
COPT | 2024-05-07 | 0 | 20240507002 | A humble request to kindly change vessel type as Cruise for MV.INSIGNIA and MV.RIVIERA | Generate Invoice/interim Invoice | Shivhar | 2024-05-07 | Closed | Mail-Vinod
COPT | 2024-05-08 | 0 | 20240508001 | upload attached IGTPL Data ( Voyage, Traffic & Invoice) for the month of April 2024 | IGPTL Upload | Shivhar | 2024-05-08 | Closed | Mail- Sajith
COPT | 2024-05-08 | 0 | 20240508002 | Change of Agent. | Generate Invoice/interim Invoice | Shivhar | 2024-05-08 | Closed | Mail-LALMON
COPT | 2024-05-09 | 0 | 20240509001 | E-invoice Error Status in Portkonnect | E Invoice | Shivhar | 2024-05-09 | Closed | Mail-Bindu Francis
COPT | 2024-05-09 | 0 | 20240509002 | Financial Analysis report not working | Financial Analysis Report | Shivhar | 2024-05-09 | Closed | viju Varghese
COPT | 2024-05-10 | 0 | 20240510001 | Marine Invoice error - SM KAVERI-INCOK124050022 | Generate Invoice/interim Invoice | Shivhar | 2024-05-10 | Closed | Mail-Ebanazer N V
COPT | 2024-05-13 | 0 | 20240513001 | IGM not listed - MT STELLAR BEVERLY ( VCN : INCOK124050052, IMO No. 9208069 ) | IGM | Venkatasagar | 2024-05-13 | Closed | Mail- Abi Mathew
COPT | 2024-05-14 | 0 | 20240514001 | SAN PRIDE - INCOK122070087 - Marine Invoice Error. | Generate Invoice/interim Invoice | Shivhar | 2024-05-14 | Closed | Ebanazer NV
COPT | 2024-05-15 | 0 | 20240515001 | Please reset the password of user-id :9055 | Users information | Shivhar | 2024-05-15 | Closed | Mail-Viju
COPT | 2024-05-15 | 0 | 20240515002 | VAILANKANNI II-BRGCP2000003 | Generate Invoice/interim Invoice | Shivhar | 2024-05-15 | Closed | Mail-LALMON
COPT | 2024-05-15 | 0 | 20240515003 | INCOK124040156 CELESTE -Final marine Invoice | Generate Invoice/interim Invoice | Shivhar | 2024-05-15 | Closed | Ebanazer NV
COPT | 2024-05-16 | 0 | 20240516001 | Berth CSLQ3 - Composite package charge - reg. | Generate Invoice/interim Invoice | Pramod | 2024-05-16 | Closed | Mail-Ebanazer N V
COPT | 2024-05-16 | 0 | 20240516002 | IGM not listed - M.T.ORIENTAL GERBERA ( VCN :INCOK124050045 , IMO No. 9924716 ) | IGM | Venkatasagar | 2024-05-16 | Closed | Mail-Naser
COPT | 2024-05-16 | 0 | 20240516003 | Change vessel type - Voyage | Vessel Profile | Shivhar | 2024-05-16 | Closed | Ebanazer NV
COPT | 2024-05-17 | 0 | 20240517001 | Fields to be extracted from Portkonnect for printing Port Users Pass | Application for Biomatric Pass | Shivhar | 2024-05-17 | Closed | Mail -Biswajith
COPT | 2024-05-18 | 0 | 20240518001 | RE: IGM VCN mapping reg...igm 2374715 dated 20.04.2024 and 2374794 dated 22.04.2024...2376221 dt 07.05.2024 | IGM | Pramod | 2024-05-18 | Closed | Mail- Baiju T.P
COPT | 2024-05-20 | 0 | 20240520001 | SERENADE OF THE SEAS-INCOK124040161 - Marine Invoice Incorrect. | Generate Invoice/interim Invoice | Shivhar | 2024-05-20 | Closed | Ebanazer NV
COPT | 2024-05-21 | 0 | 20240521001 | VAILANKANNI II-BRGCP2000003 | Generate Invoice/interim Invoice | Shivhar | 2024-05-21 | Closed | Lalmon NK
COPT | 2024-05-22 | 0 | 20240522001 | Fields to be extracted from PortKonnect for printing Port Users Pass | Application for Biomatric Pass | Shivhar | 2024-05-22 | Closed | Mail -Biswajith
COPT | 2024-05-22 | 0 | 20240522002 | Portkonnect SAP Status Issue-rreg. | SAP | Pramod | 2024-05-22 | Closed | viju Varghese
COPT | 2024-05-27 | 0 | 20240527001 | INCOK124050102 WAN HAI 501 Main Line - vessel. | Estimation Invoice | Shivhar | 2024-05-27 | Closed | Ebanazer NV | [10 empty] | 2024-05-27
COPT | 2024-05-27 | 0 | 20240527002 | Vessel not available for Voyage Registration screen | VoyageRegistrations | Pramod | 2024-05-27 | Closed | viju Varghese | [10 empty] | 2024-05-27
COPT | 2024-05-29 | 0 | 20240529001 | Duplicate Vehicles scanned for Gate in | List of Vehicles scanned for Gate in | Pramod | 2024-05-29 | Closed | Mail -Biswajith | [10 empty] | 2024-05-30
COPT | 2024-05-30 | 0 | 20240530001 | IDLING BERTH HIRE CHARGES | Voyagemonitoring | Pramod | 2024-05-30 | Closed | N.K. LALMON | [10 empty] | 2024-05-30
COPT | 2024-05-31 | 0 | 20240531001 | BEYPORE SULTAN - 9711664 Not available for Voyage Registration - URGENT!! | PCS | Pramod | 2024-05-31 | Closed | viju Varghese | [10 empty] | 2024-05-31
COPT | 2024-05-31 | 0 | 20240531002 | Ticket#202405310000039 — <TypeOfCargo>xx</TypeOfCargo> node value Reg | VoyageRegistrations | Shivhar | 2024-05-31 | Closed | viju Varghese | [10 empty] | 2024-06-05
COPT CFS | 2024-05-31 | 0 | 20240531003 | IGM is not available in IGM VCN screen | IGM VCN Mapping | Sai Prassana | 2024-05-31 | Closed | Mail- Baiju T.P | 2024-05-31 | NA | 2024-05-31
COPT CFS | 2024-05-31 | 0 | 20240531004 | EXport storage invoice for RI74320 missing | Export Storage | Srikanth | 2024-05-31 | Closed | Mail- Baiju T.P | 2024-06-03 | NA | 2024-06-03
COPT CFS | 2024-06-03 | 0 | 20240603001 | Ramp Examption MSNU3049339 | Import | Gayathri | 2024-06-03 | Closed | Whatsup - Baiju |  | RCA need to be provided
COPT CFS | 2024-06-03 | 0 | 20240603002 | Ramp Examption MEDU6105526 | Import | Gayathri | 2024-06-03 | Closed | Whatsup - Baiju |  | RCA need to be provided
COPT CFS | 2024-06-03 | 0 | 20240603003 | Lift on Charges missing | Stacker charges | Gayathri | 2024-06-03 | Closed | Mail- Baiju C.P |  | RCA need to be provided | 2024-06-04
COPT CFS | 2024-06-03 | 0 | 20240603004 | Import charges Destuffing CAIU7950455 | Destuffing | Sai Prassana | 2024-06-03 | Closed | Prajeev | 2024-06-04 | RCA need to be provided
COPT | 2024-06-04 | 0 | 20240604001 | Change of Agent- MV SRI ANJANA-INCOK121120131 | Generate Invoice/interim Invoice | Pramod | 2024-06-04 | Closed | Lalmon NK | [10 empty] | 2024-06-04
COPT | 2024-06-05 | 0 | 20240605001 | IGM details are not being reflected in the IGM listing. | PCS File Process | Pramod | 2024-06-05 | Closed | Abi Mathew | [10 empty] | 2024-06-05
COPT | 2024-06-05 | 0 | 20240605002 | RE: VCN INCOK124050162 - ATA OCEAN - for vcn cacellation. | Generate Invoice/interim Invoice | Pramod | 2024-06-05 | Closed | Ebanazer NV | [10 empty] | 2024-06-05
COPT | 2024-06-06 | 0 | 20240606001 | Deletion of Fresh water charge for COINGF24ST05660 | Generate Invoice/interim Invoice | Shivhar | 2024-06-06 | Closed | lalmon NK | [10 empty] | 2024-06-06
COPT | 2024-06-06 | 0 | 20240606002 | VCN050133 OCEAN FAYE shifting update in Shipping program | Shipping Program | Bhavanishankar | 2024-06-06 | Closed | Rajani | [10 empty] | 2024-06-06
COPT CFS | 2024-06-06 | 0 | 20240606003 | User login issue | Functional | Gayathri | 2024-06-06 | Closed | Customer | 2024-06-06 | NA | 2024-06-06
COPT CFS | 2024-06-06 | 0 | 20240606004 | Interim invoice | Export Cargo | Sharath | 2024-06-06 | Closed | Mail- Baiju T.P | 2024-06-11 | NA
COPT | 2024-06-07 | 0 | 20240607001 | XIN LIAN YUN GANG - vcn request in voyage registion - PortKonnect | VoyageRegistrations | Pramod | 2024-06-06 | Closed | Ebanazer NV | [10 empty] | 2024-06-07
COPT | 2024-06-07 | 0 | 20240607002 | Kindly change the commodity code for the vessel INCOK124050153 | Supplementary Service request | Shivhar | 2024-06-07 | Closed | Nasar C H | [10 empty] | 2024-06-07
COPT | 2024-06-07 | 0 | 20240607003 | VCN050133 OCEAN FAYE sailing update in Shipping program | Shipping Program | Shivhar | 2024-06-07 | Closed | Rajani | [10 empty] | 2024-06-07
COPT | 2024-06-07 | 0 | 20240607004 | same truck is coming up once scanning is done at Cochin Port Authority Ekm Wharf In-Gate | Scanned QR CODE for Gate in | Pramod | 2024-06-07 | Closed | viju Varghese | [10 empty] | 2024-06-10
COPT | 2024-06-10 | 0 | 20240610001 | THINNAKARA-INCOK123080064 | Generate Invoice/interim Invoice | Shivhar | 2024-06-10 | Closed | lalmon NK | [10 empty] | 2024-06-11
COPT | 2024-06-10 | 0 | 20240610002 | LPG Handling at MULT by IOCL | E-Invoice | Pramod | 2024-06-10 | Closed | viju Varghese | [10 empty] | 2024-06-10
COPT | 2024-06-10 | 0 | 20240610003 | Requested to change ATA for INCOK124060002 | Voyage Monitoring | Shivhar | 2024-06-10 | Closed | Rajani | [10 empty] | 2024-06-10
COPT CFS | 2024-06-10 | 0 | 20240610004 | Storage Invoice | Export Cargo Stuffing | Sharath | 2024-06-10 | Closed | Mail-Baiju TP | 2024-06-10 | NA | 2024-06-10
COPT | 2024-06-11 | 0 | 20240611001 | In Service Recording Screen verification showing "ERROR" for VCN INCOKI 2405139 ROSE GAS | Service Recording | Pramod | 2024-06-11 | Closed | Rajani | [10 empty] | 2024-06-11
COPT | 2024-06-12 | 0 | 20240612001 | BUNKER REQUEST CANCELLATION LETTER - ATA OCEAN [INCOK124050162] | Supplementary Service request | Shivhar | 2024-06-12 | Closed | Nasar C H | [10 empty] | 2024-06-12
COPT CFS | 2024-06-18 | 0 | 20240618001 | Wrong mapping of SB to RI- Deletion of SB | Error | Sharath | 2024-06-18 | Closed |  | 2024-06-18 | NA | 2024-06-18
COPT | 2024-06-18 | 0 | 20240618002 | Requestet to change GRT for INS VIKRANT | Generate Invoice/interim Invoice | Shivhar | 2024-06-18 | Closed | Dinesan MK | [10 empty] | 2024-06-19
COPT CFS | 2024-06-19 | 0 | 20240619001 | New Agent-OZONE CARGO |  | Sharath | 2024-06-19 | Closed | Mail-Baiju TP | [10 empty] | 2024-06-19
COPT | 2024-06-20 | 0 | 20240620001 | IGM not listed for MT SUNNY MARK (INCOK124060068) | IGM | Pramod | 2024-06-20 | Closed | Abi Mathew | [10 empty] | 2024-06-20
COPT | 2024-06-20 | 0 | 20240620002 | Correction option in Capture Arrival/ Departure | Capture Arrival/ Departure |  | 2024-06-20 | Closed | Rajani
COPT | 2024-06-20 | 0 | 20240620003 | SLAB has been added for shifting (LAKSHADWEEP SEA-INCOK123120002) | Generate Invoice/interim Invoice | Shivhar | 2024-06-20 | Closed | lalmon NK | [10 empty] | 2024-06-21
COPT | 2024-06-21 | 0 | 20240621001 | Not able to process Voyage Registration file - CALINF : 9512202 | PCS | Pramod | 2024-06-21 | Closed | viju Varghese | [10 empty] | 2024-06-21
COPT | 2024-06-24 | 0 | 20240624001 | DISCREPANCY IN SHIFTING CHARGE - HSC. CHERIYAPANI-INCOK124050112 - | Generate Invoice/interim Invoice | Shivhar | 2024-06-24 | Closed | lalmon NK | [10 empty] | 2024-06-24
COPT | 2024-06-24 | 0 | 20240624002 | SRI ANJANA-INCOK121120131- CHANGE OF AGENT | Generate Invoice/interim Invoice | Shivhar | 2024-06-24 | Closed | lalmon NK | [10 empty] | 2024-06-24
COPT CFS | 2024-06-25 | 0 | 20240625001 | Gang Demanded and Allocated wrongly for Gang Plan | Functional | Sharath | 2024-06-25 | Closed | Whatsapp-Baiju TP | 2024-06-25 | NA | 2024-06-25 | [7 empty] | 2024-06-25
COPT | 2024-06-25 | 0 | 20240625002 | Berman' failed status -16.06.2024 to 26.06.2024) | PCS | Pramod | 2024-06-25 | Closed | Vinod
COPT | 2024-06-28 | 0 | 20240628001 | Change GRT for INS VIKRANT | Finace | Shivhar | 2024-06-28 | Closed | Dinesan MK | [10 empty] | 2024-06-28
COPT | 2024-07-01 | 0 | 20240701001 | RE: Multiple records for the same truck | Gate | Shivhar | 2024-07-01 | Closed | viju Varghese | [10 empty] | 2024-07-01
COPT | 2024-07-02 | 0 | 20240702001 | Shifting to CSL Repair dock on 23.06.2024 for VCN 23040095 IND SUJATHA |  | Shivhar | 2024-07-02 | Closed | Rajani | [10 empty] | 2024-07-02
COPT | 2024-07-02 | 0 | 20240702002 | Upload IGM List for VCN 23040095 IND SUJATHA | IGM | Shivhar | 2024-07-03 | Closed | Rajani | [10 empty] | 2024-07-02
COPT | 2024-07-03 | 0 | 20240703001 | Request for changing Agent Name | Generate Invoice/interim Invoice | Shivhar | 2024-07-03 | Closed | Dinesan MK | [10 empty] | 2024-07-03
COPT | 2024-07-05 | 0 | 20240705001 | Boat crew Pass issue | Boat crew Pass | Shivhar | 2024-07-05 | Closed | viju Varghese | [10 empty] | 2024-07-05
COPT | 2024-07-08 | 0 | 20240708001 | RE: THINNAKARA-INCOK123080064 | Generate Invoice/interim Invoice | Shivhar | 2024-07-08 | Closed | lalmon NK | [10 empty] | 2024-07-08
COPT | 2024-07-08 | 0 | 20240708002 | RE: Voyage Registration file handling issue. | PCS | Shivhar | 2024-07-08 | Closed | viju Varghese | [10 empty] | 2024-07-08
COPT | 2024-07-09 | 0 | 20240709001 | RE: Validating the status of ICGS Vessels to Parked - reg. | Generate Invoice/interim Invoice | Shivhar | 2024-07-09 | Closed | Dinesan MK | [10 empty] | 2024-07-09
COPT | 2024-07-10 | 0 | 20240710001 | Pre Berthing delay reason wrongly marked NON AVAILABILITY OF BERTH for VCN 24070003 WAN HAI 501 |  | Shivhar | 2024-07-10 | Closed | Rajani | [10 empty] | 2024-07-10
COPT | 2024-07-12 | 0 | 20240712001 | RE: Diversion of MT Pagos - release of parked amount | Generate Invoice/interim Invoice | Shivhar | 2024-07-12 | Closed | Nasar C H | [10 empty] | 2024-07-12
COPT | 2024-07-12 | 0 | 20240712002 | RE: Fields to be extracted from PortKonnect for printing Port Users Pass | Photo copies | Shivhar | 2024-07-12 | Closed | Mail -Biswajith | [10 empty] | 2024-07-12
COPT | 2024-07-16 | 0 | 20240716001 | Requested to change Pilot cancellation date for JAG PAVITRA INCOK124070056 | Generate Invoice/interim Invoice | Shivhar | 2024-07-16 | Closed | Ebanazer NV | [10 empty] | 2024-07-16
COPT | 2024-07-16 | 0 | 20240716002 | Shifting showing error for VCN 24070047 ICGS SAMARTH | Service request | Shivhar | 2024-07-16 | Closed | Rajani | [10 empty] | 2024-07-16
COPT | 2024-07-19 | 0 | 20240719001 | RE: Multiple records for the same truck FOR KL27D9087 | Gate | Shivhar | 2024-07-19 | Closed | viju Varghese | [10 empty] | 2024-07-19
COPT | 2024-07-19 | 0 | 20240719002 | Fields to be extracted from PortKonnect for printing Port Users Pass | Photo copies | Shivhar | 2024-07-22 | Closed | Biswajith | [10 empty] | 2024-07-22
COPT | 2024-07-22 | 0 | 20240722001 | RE: Tank Farm Details |  | Shivhar | 2024-07-22 | Closed | Biswajith | [10 empty] | 2024-07-22
COPT | 2024-07-22 | 0 | 20240722002 | IGM VCN Issue related to primary key violation | PCS File error | Sharath | 2024-07-23 | Closed | Baiju TP | 2024-07-24 | [9 empty] | 2024-07-23
COPT | 2024-07-29 | 0 | 20240722003 | IGM VCN mapping reg...2383760 DT 27.07.2024 | Multiple file processing of IGM files | Sharath | 2024-07-29 | Closed | Baiju TP | 2024-07-30 | [9 empty] | 2024-07-30
COPT | 2024-07-29 | 0 | 20240722004 | Destuffing Container EGHU3869557 IGM No 2382577 | Destuffing Issue | Sharath | 2024-07-31 | In Progress | Prajeev
COPT | 2024-07-30 | 0 | 20240722005 | Invoices are not generating | Invoices generation | Sharath | 2024-07-30 | Closed | Baiju CP | 2024-07-30 | [9 empty] | 2024-07-30
COPT | 2024-07-30 | 0 | 20240722006 | Lift on Recording done for Cont. BEAU6391785 Invoice not generated. | Invoices generation | Sharath | 2024-07-30 | In Progress | Baiju CP | 2024-07-31
Formulas:
Aging in Days = IF(Table2[[#This Row],[Status]]="Closed",0,(TODAY()-Table2[[#This Row],[Received]]))

## CUSTOMER PORTAL
CFS POS for Customer Portal( Data should be provided only according to user credentials)
Sl.No | Main Menu | Sub Menu | Responsible | Proposal | CFS Remarks |  | NIT Status | CFS Remark 15 07 2024
3 | Export (Cargo) | RI List | Agent (CHA) | "Provide the RI list to customers so they can see all the details of the RI submitted by them, including 'cargo receipt status' (number of packages and date of receipt at CFS), with a filter provision. Data should be restricted according to user credentials." | Pending (Prioritize for automation) | User credential based access to list of RI is to be provided. The customer should be able to know all the RI related data including Receipt date & time, Quantity & Location if the cargo is received by CFS. (Multiple receipt date & time against one RI are to be listed) | Closed | Checked in QA and confirmed everything, except that the label name in the customer portal should be changed to 'RI LIST' instead of 'RI Info'.
4 | Export (Cargo) | SB RI Mapping | Agent (CHA/ Console Agent) | To provide two fields for total cargo receipt quantity and No of packages in SB RI mapping screen. If there is any mismatch in quantity and No of packages in Cargo Receipt with SB, system will not allow customers to submit records. Customers approach the CFS authority to resolve the discrepancy. | Pending (Prioritize for automation) | At present, total cargo receipt quantity and no. of packages are not available in the screen provided for SB - RI mapping. The same needs to be provided. At present the validation is limited with SB & RI quantity. In addtion to the present validation, the cargo receipt quantity should be the same as that of SB & RI quantity should also be validated. If SB is available in PortKonnect, provision to map sb with RI to be provided to the customer. Otherwise the mapping should only be done by CFS officials. | Closed | The indefinite decimal points in the cargo receipt hinder mapping. Mr. T.P Baiju sent the details of the discrepancy through WhatsApp to Mr. Sharath
5 | Export (Cntr.) | Container SB RI Mapping | Agent (CHA/ Console Agent) | To rename as "Factory Stuff Cont. SB RI Map". To generate notification for Approval/Rejection with remarks | RI Create for Factory Stuffing |  | Closed | Pending
6 | Export (Container) | Stuffing Request | Agent (CHA/ Console Agent) | "Generate a notification for approval by CFS once a request is submitted by agents. NB: By default, the chargeable party will be the same 'CHA/Agent'. If any changes are required in the chargeable party, agents should approach the CFS authority for updating the chargeable party, and a provision should be made for uploading the relevant documents." | Pending (Prioritize for automation) | The present screen for the stuffing request will be provided to the agent with a provision to upload the affidavit of chargeable party in pdf format, change if any, in the chargeable party. The restriction of the records should be based on the customer. Notification to be provided to the CFS officials once the request is created by the agent. The CFS official will have the provision to approve or reject with remarks. (Similar to RI). | Closed | In Progress
7 | Export (Container) | View-Stuffing Request | Agent (CHA/ Console Agent) | "Provide the total quantity and number of packages, and include a print option on the screen." | Pending (Prioritize for automation) | Details of stuffing Request needs to be downloaded in pdf format along with summary of the quantity/package by the agent. The summary should also be provided in the Stuffing Request screen in the main grid. | In Progress | In Progress
8 | Back to Town (Cargo) | Capture BTT | Agent (CHA) | Screen name to be changed as "Request for BTT". | Pending |  | Closed | Checked in QA and satisfied
9 | Lift On / Off Operation | Lift Off Request | Agent (CHA/ Console Agent/Mech.Foreman) | The agent request for container Lift Off . 1. To provide a column for if Plug In required (Y/N) in both Export and Import screen. 2.Chargeable party field active only for CFS.3.Upload provision for document .4.Container selection to be changed with IGM/VCN/VSL/VOY .5.Container selection through grid and add button .6. A Check button against each container selected for the Mech.Foreman to record work done status and other fields are only for view to Mech Foreman.7.Chargeable party field by default the requesting Agent and not editable to the Agent.8. To generate notification for Rejection with remarks to the customer for re submission and notification for the approved ones only to Mech.Foreman | Pending |  | Closed | Pending
10 | Lift On / Off Operation | View Lift Off Request | Agent (CHA/ Console Agent/Mech.Foreman) | 1.Viewing similar to Lift off request propsal.Additional column for the work done status and hold status.2.Mech.Foreman can view those approved requests where he has recorded the workdone status. | Pending |  | Closed | Pending
11 | Buffer Yard | Buffer Yard | Agent | The agent request for Buffer Yard Opertaion. To generate notification for Approval/Rejection with remarks and notification sent to the customer | Pending |  | Closed | Checked in QA and satisfied
12 | Weighment | Weightment Request | Agent | The agent request for weighment. To generate notification for Approval/Rejection with remarks | Pending |  | Closed | Checked in QA and satisfied
13 | Import | Mark enbloc | Agent (Lines) | 1. If Shipping Line is assigning a ‘CHA/Agent’ and a notification sends to concerned CHA/Agent. Provision to be made to ‘CHA/Agent’ for movement request to CFS authority by notification. CFS authority approves the request and ‘CHA/Agent’ will be able to printout the movement request. (NB:- By default, the chargeable party wiil be the same 'CHA/Agent' assigned by the Shipping Line. If any changes are required in the Chargeable Party, they should approach the CFS authority for updating Chargeable Party and provision should be made for uploading their relevant documents. 2.If Shipping Lines required for ‘Enbloc Movement’, notification comes to CFS authority and CFS assigned a transporter and notification send to the transporter. An additional field in this screen to be provided which will be activated only for CFS for assighning to the CFS transpoter . The transporter should be able to update Vehicle/ Driver details in “Capture Trailer Details” 3. To provide a column for Shipping Line Code in grid. The Shipping Line Code to be obtained from the Shipping Line Master. (No ‘Shipping Line Master’ in existing system. To discuss with CoPA EDP for ‘Shipping Line’ data) 4."Edit" option in the 'Mark enblock 'screen need not be available to the Customer/user | Pending |  | Pending | Pending
14 | Import | Capture Trailer Detail | Agent (CHA/ Console Agent) | "CHA/Agent is only able to update trailer, driver, and license details." | Pending (Prioritize for automation) | Needs to be provided to agent. | Closed | In Progress
15 | Import | Destuffing Request | Agent (CHA/ Console Agent) | "Change the screen name to 'Destuffing / Ramp Exam Request'. The Chargeable Party name will default to CHA/Agent, and the logged-in user (CHA/Agent) cannot modify this. The screen requires a document upload feature to submit Customs approval for destuffing." | Pending (Prioritize for automation) | Needs to be provided to agent. The screen name should be 'Destuffing / Ramp Exam Request' with a provision to upload the affidavit of chargeable party in pdf format, change if any, in the chargeable party. The restriction of the records should be based on the customer. Notification to be provided to the CFS officials once the request is created by the agent. The CFS official will have the provision to approve or reject with remarks. (Similar to RI). | Closed | In Progress
16 | Import | Capture Delivery Truck Details | Agent (CHA/ Console Agent) | No modifications are required on the screen for cargo delivery. | Pending (Prioritize for automation) | Needs to be provided to agent. | Closed | In Progress
17 | Import/ Export | Capture Empty Trailer Details | Agent (CHA/ Console Agent) | No modifications are required on the screen for Container Gate Out | Pending (Prioritize for automation) | Needs to be provided to agent. | Closed | Pending
18 | Import | Removal Form | Agent (CHA/ Console Agent) | For Print out 'Removal Form' (Data should be restricted as per user credential) | Pending |  | Closed | Pending
19 | Import | SEZ Report | Agent (CHA/ Console Agent) | For Print out 'SEZ-04' (Data should be restricted as per user credential) | Pending |  | Closed | Pending
20 | Transshipment | Create Transshipment | Agent (CHA/ Console Agent) | "Change the screen name to 'Transshipment Request'. Notifications for approval or rejection will be sent to the CFS authority. The logged-in user is the Chargeable Party by default, and the Chargeable Party cannot be changed." | Pending (Prioritize for automation) | "Change the screen name to 'Transshipment Request'. Notifications for approval or rejection will be sent to the CFS authority. Edit option to be provided to CFS officials. The logged-in user is the Chargeable Party by default, and the Chargeable Party cannot be changed." | Closed | In Progress
21 | Fork Lift | Fork Lift Request | Agent (CHA/ Console Agent/Mech.Foreman) | 1.A"Chargeable Party " field and Remarks field to be incorpoated which is active only for CFS.2. "Submit" button to be changed as "Request".3.An additional check box for"workdone status" for the Mech.Foreman to record and he can only view other fields .3.As per notification recd from Customer , approval/Reject with remarks by CFS to customer and only approved request notification to Mech.Foreman. | Pending |  | Closed | Unable to check. Provision for the mechanical department has not been provided
22 | Fork Lift | Forklift individual report | Agent (CHA/ Console Agent/Mech.Foreman) | 1.Screen name to be changed as “ Fork Lift Truck Hire Report”. (Data should be restricted as per user credential.2.An additional column of "Work done status " to be incorporated to indicate status recorded by Mech.Foreman and he can view the list of approved ones where he has recorded the work done status. | Pending |  | Closed | Checked in QA and satisfied, except for the work done status, which has not been provided
23 | Import | ADO For Cargo | Agent (CHA/ Console Agent) | To modify the 'ADO for Cargo' screen before providing it to the Customer Portal with user restrictions, the following modifications are planned: 1. This screen is intended for Console Agents and CHAs. 2. For Console Agents and CHAs, include a mandatory field to upload the ADO for cargo to the respective CHA intending to take delivery. Notifications will be sent to the concerned CHA, who can view the uploaded ADO from the Console Agent or CHA. 3. For CHAs receiving the ADO, provide a field to view the submitted data by the Console Agent or CHA, add remarks if necessary, and submit it as a request for an Appraisement Ticket to CFS using the 'Appr. Request' button. 4. CFS will approve or reject the Appraisement Ticket with remarks based on notifications received from the CHA. 5. CHAs can print the approved Appraisement Ticket only from the 'Appraisement List' screen." | 80% completed in Quality ((Prioritize for automation)) |  | Closed | This has already been provided in production, and we have verified with customer credentials that it is working fine.
24 | Import | Appraisement List | Agent (CHA/ Console Agent) | "Provide an 'Appraisement List' to customers to view all details of ADO and Appraisement submitted by them, with a filter provision (restricted by user credentials). Add a 'Status' field (approved or rejected) alongside existing fields. CHA/Console agents can view all their approved/rejected ADO/Appraisement from this screen. CHA can only print approved Appraisement Tickets from the 'Appraisement List' screen. Additionally, include an identification column in the Appraisement List for GC Container/UB Container/General Cargo/UB Cargo." | 80% completed in Quality ((Prioritize for automation)) |  | Closed | This has already been provided in production, and we have checked with customer credentials; it is working fine. The printable area for the 'Appraisement Ticket' now exceeds one page and needs to be fixed to fit on one page.
25 | Import | ADO (Container) | Agent (Shipping Line/Console Agent/CHA) | To modify the 'ADO' screen for containers before providing it to the Customer Portal with user restrictions. Modifications are as follows: 1. Change the screen name to 'ADO for Container'. 2. Make this screen accessible to Shipping Lines and CHAs (currently not available to Shipping Lines). 3. For Shipping Lines, include a feature to issue ADO to the concerned Console Agent/CHA. 4. For Console Agents/CHAs, allow them to request an Appraisement Ticket for Destuffing/Onwheel Examination from CFS. 5. CFS will approve or reject the Appraisement Ticket with remarks based on notifications received from CHAs/Console Agents. 6. Console Agents/CHAs can print approved Appraisement Tickets only from the 'Appraisement List'. 7. Add an additional column in the Appraisement List to identify GC Container, UB Container, GC Cargo, and UB Cargo. | Pending (Prioritize for automation) |  | In Progress | In Progress

## Customer Portal Summary
Customer Portal |  | Remarks
Closed | 20
In Progress | 2
Pending | 1
Total | 23