## List of On Going issues.
Sl No | Issue Summary | Reported Date | Stake holder | Priority | Bug ID | Status | Target Date | Remarks | QA status/Remarks
1 | User is unable to login the application both admin and end user | 2024-08-12 | Quixy-Sharath | High | NA | Closed | 2024-08-12 |  | Closed
2 | Webhook, billing integration, External App reference-Allowing all PoS API services hosted in 10.10.90.157 server to be allowed in 10.10.100.133-----> IGM VCN Mapping, PCS Files Processing and Invoice Generation issue. | 2024-08-12 | Ctrls Team | High | NA | Closed | 2024-08-14 | Ctrls Team blocked the Billing URL's and they are working on it. | Ctrls team need to check
3 | Getting error message"42703: Cloumn 14122019 -105714917-a909fcfa -f15b-4cb0-b02f-a767b88b2366,SubLine does not exist POSITION:11301" while submiting the add record | 2024-08-12 | Sharath | Medium | NA | Closed | 2024-08-12 | Sharath- Updated the get functions from where the subline is changed sub line no and updated the app. | Closed
4 | Update App data function is not working in EDIT RI and EDIT Cargo Receipt Screens. | 2024-08-12 | Sharath | High(P3) | QXY-35304 | Closed | 2024-08-14 | For smooth flow of CFS operations . We are updating the data from backend as per Baiju TP request until the issue is resolved. | Issue will be fixed by today(14-08-2024), will plan the build to QA and staging on Monday, after the CS team clearance patch will be deployed to copt prod
5 | SB RI mapping is taking atleast 15-20 s to submit and for some RI's the SB No's are not getting mapped.-Add and Update app data function is not working as expected. | 2024-08-13 | Sharath | High(P1) | QXY-35328 | Closed | 2024-08-21
6 | IGM VCN Mapping Update app data functionality is not working with Voyage No containing Alphabets like 093W. | 2024-08-14 | Sharath | High(P1) |  | Closed | 2024-08-21 | RCA is that the voyage No containing alphabets like "199W" are not updating from add record page of IGM VCN Mapping and other Voyage No like "1925" is getting updated from the app.
7 | Add App data function is not working in Capture Trailer Details App. | 2024-08-20 | Sharath | High(P2) |  | Closed | 2024-09-03 | This issue is being checked with Baiju CP on anydesk and it is working as expected.
8 | Duplication of SB No in Export Tally Recording | 2024-09-24 | Sharath | High(P1) |  | Closed | 2024-09-25
9 | After VCDT Partial Delivery charges are not reflecting | 2024-09-03 | Sharath | High(P1) |  | Closed | 2024-09-06 | Cnfirmed by George James.
10 | Stuffing Charges and Storage Charges are not reflected as invoices are not generated | 2024-09-02 | Sharath | High(P1) |  | Closed | 2024-09-03
11 | Some RI's are not available in "Cargo receipt" and "Gate In" screen.But the same is available in RI List .So we forced to create new RI to complete. | 2024-09-04 | Sharath | High(P1) |  | Closed | 2024-09-05
12 | Container No ASLU7034635 Updated in Update Line Sub line but not reflecting in Tally Recording. | 2024-09-06 | Sharath | High(P1) |  | Closed | 2024-09-24 | Ready in staging and unit testing is pending from NIT.
13 | TSA No-TSA2402806 is not reflecting in Gate In and Gate Out. | 2024-09-06 | Sharath | High(P1) |  | Closed | 2024-10-10 | Need to take the requirement from CFS Team and Close it.
14 | Invoice Generation of TSA No TSA1904919 | 2024-09-10 | Sharath | High(P1) |  | Closed | 2024-09-12 | Need to connect with NIT on invoices issue.
14 | CFS Invoices are not getting generated in COPA-CFS. | 2024-09-18 | Sharath | High(P1) |  | Closed | 2024-09-18
15 | Count of Data Entry from 1st Sep to 30th Sep by user wise | 2024-09-25 | Sharath | Medium(P1) |  | Closed | 2024-11-13 | Module wise Priority to give the screens with app report on user wise.
16 | Doubling of RI 80797 in Cargo Receipt | 2024-09-23 | Sharath | Medium(P2) |  | Closed | 2024-09-25
17 | Invoices are not generating in CFS with Tally Recording with only half of invoices are generating. | 2024-09-18 | Sharath | High(P1) |  | Observation | TBD |  | From last week after deployment on 08-10-2024 need to check for more 10 days to monitor and close
18 | Issues in container Gate Out reg.. | 2024-10-01 | Sharath | High(P1) |  | Closed | 2024-10-06
19 | Gate out time update issue reg.. | 2024-10-15 | Sharath | High(P1) |  | Closed | 2024-10-15
20 | TLLU823585 7 20' A/c All Cargo logistics. There are 6 S.B. with the container and all of them have storage charges. But the storage invoice are generated with 4 SB only. Stuffing invoice and storage invoice for RI81760&82190 are not generated. | 2024-10-19 | Sharath | High(P1) |  | Closed | TBD |  | From last week after deployment on 08-10-2024 need to check for more 10 days to monitor and close
21 | Export tally recording done for a 20 feet container TEMU1616193 with 02 Shipping Bill | 2024-10-22 | Sharath | High(P1) |  | Closed | TBD |  | From last week after deployment on 08-10-2024 need to check for more 10 days to monitor and close
22 | RI 82362 and RI 82375 created on 16.10.2024 is not available in cargo receipt screen. Both are available in "Gate In/Out" screen | 2024-10-16 | Sharath | High(P1) |  | Closed | 2024-10-22
22 | Issue in RI after the version updation | 2024-10-26 | Sharath | High(P1) |  | Closed
23 | Export tally recording done for a 20 feet container UACU3790328 with 09 Shipping Bill. .After tally recording applicable charges has not generated completely . 02 storage (RI 83040 & 83005) and stuffing charge need to be generate.Pls check and do the needful as earliest. | 2024-11-05 | Sharath | High(P1) |  | Closed | TBD
24 | User- 1005114 is not able to login. | 2024-11-12 | Sharath | Medium(P1) |  | Closed | 2024-11-13
25 | ADO container is not available after tally Recording | 2024-11-12 | Sharath | High(P1) |  | Closed | 2024-11-13
26 | Container No. TCKU1047003 IGM No.2392476 not available in Destuffing Tally Recording. | 2024-11-12 | Sharath | High(P1) |  | Closed | 2024-11-14
27 | Stuffing charge invoices reg...Cntr GCXU5455920 | 2024-11-26 | Sharath | High(P1) |  | Closed | 2024-11-27 | Need to update the status of the Container as Tally Completed.
28 | Clearance for gate out of container ECNU2269704 reg.Stuffing charge invoice generated correctly. But in "Clearance for Gate out" screen the container is not available.Hence clearance for the same is not done.Please check and do the needful. | 2024-11-25 | Sharath | High(P1) |  | Closed | 2024-11-27
29 | RI84152 not available for SB RI mapping. | 2024-11-23 | Sharath | High(P1) |  | Closed | 2024-11-25
30 | Add New Exporter Name | 2024-11-22 | Sharath | Medium(P1) |  | Closed | 2024-11-25
31 | Invoice for Lift on & Lift off (Laden) | 2024-11-21 | Sharath | High(P1) |  | Closed | 2024-11-25
32 | Gate out date update reg.. | 2024-12-04 | Sharath | High(P1) |  | Closed | 2024-12-12
33 | SEKU5978917 40 IGM No 2393274 container not available in Destuffing Request Screen. | 2024-12-02 | Sharath | High(P1) |  | Closed | 2024-12-03
34 | Manual Invoice for Import Storage Charges | 2024-12-06 | Sharath | High(P1) |  | Closed | TBD with George |  | Script need to be executed in the Production
35 | TSA No is not displaying in Invoices list in Billing Module | 2024-12-09 | Sharath | High(P1) |  | Closed
36 | Cntr TCNU6045292 not available for Gang Plan… | 2024-12-07 | Sharath | High(P1) |  | Closed | 2024-12-09
37 | Invoice Raised Without Manual Intervention reg.. | 2024-12-06 | Sharath | High(P1) |  | Closed |  |  | TBD with Pramod and COPT Team to close
38 | Cntrs lying in Gang plan list reg | 2024-12-05 | Sharath | High(P1) |  | Closed | 2024-12-09
38 | IGM not available for mapping reg.. | 2024-12-11 | Sharath | High(P1) |  | Closed | 2024-12-19 |  | CFS Team/Viju sir need to confirm whether the missed tags are necesssary or not.
39 | Three export containers invoices not getting after tally recording,updated in system. TCNU7541002 ,SEGU6594608 & CXDU1279518 | 2024-12-26 | Sharath | High(P1) |  | Closed | 2025-01-23
40 | Back to town cargo storage invoice not getting for RI 67117 | 2024-12-24 | Sharath | High(P1) |  | Closed | 2025-01-03
41 | CONTAINER NO. TCKU 3488543 20 FT AND C.NO TCNU 6156906 40FT WHICH WAS DESTUFFED ON 11TH DECEMBER | 2024-12-24 | Sharath | High(P1) |  | Closed
42 | IGM 1115979 dt 23.12.2024 posted in POS but still not available for mapping | 2024-12-24 | Sharath | High(P1) |  | Closed | 2025-01-02
43 | container No INKU6147407 is not available in gate in, upto capture trailer is submitted already. | 2024-12-30 | Sharath | High(P1) |  | Closed | 2025-01-03
44 | IGM PCS-401- unauthorized error after posting to CFS | 2024-12-31 | Sharath | High(P1) |  | Closed | 2024-12-31
45 | IGM 1116766 dt 30.12.2024 IGM 1117417 dt 03.01.2025 | 2025-01-08 | Sharath | High(P1) |  | Closed | 2025-01-08
46 | CONTAINER NOT AVAILABLE IN DESTUFFING REQUEST REGARDING- 1. CXDU 177377-3 20FT 2. DRYU 261278-0 20FT 3. GAOU 207795-4 20FT 4. FFAU 102018-4 40FT 5. SSVU 700042-2 20FT | 2025-01-22 | Sharath | High(P1) |  | Closed | 2025-01-31
47 | Add containers reg.. IGM 1117010 dt 31.12.2025 | 2025-01-29 | Sharath | High(P1) |  | Closed | 2025-02-05 | Need clarification from cfs Team and Schedule a meeting with baiju tp on the new screen approach on amendment of containers in the IGM pcs file-20-02-2025. 11:30 AM
48 | Due to the non availabliliy of Import container TRHU1869889 20' in system we are un able to generate invoices for the services provided to the said container.Hence it is requsted that please provide manual invoices for De-stuffing, Lifit off (Ldd) & Lift on (Empty) as per below details. | 2025-02-12 | Sharath | High(P1) |  | Closed | 2025-02-13
49 | Lift on recording was done for container no.EGHU9244485 (40' Empty) of M/s A A Abdul Azeez.(1000646),invoice not generated, IGM No.1120342 Dt.24.01.2025,Vessel Ever Brace- 101E, Pls | 2025-02-06 | Sharath | High(P1) |  | Closed | 2025-02-12
50 | IGM1121652 dt 03.02.2025 not available in " Import General Manifesto View " screen | 2025-02-19 | Sharath | High(P1) |  | Closed | 2025-02-19
51 | Lift on recording done for Cont. no.UACU3130237 (1x20', Empty) of M/s. National Trades & Agencies (1002244), invoice not generated.IGM no.1122127,Vessel SSL Bharath -171C. | 2025-03-03 | Sharath | High(P1) |  | Closed | 2025-03-05
52 | Cont.nos. WHSU2326883 & WHSU2499343 Size- 20'(LADEN) CHA M/s.ISB lOGISTICS INDIA PRIVATE LTD (A//c no.1003659) Service- Lift off & Lift on (Laden) Lift on Date: 01-02-2025 Time:12:00 p.m. Lift off Date :01-12-2025 Time: 12:15 p.m. Vessel-WAN HAI 515- 096E IGM No.1116766 , Dated:30-12-2024 VCN No.INCOK124120155 | 2025-03-03 | Sharath | High(P1) |  | Closed | 2025-03-05
53 | THE DETAILS OF THE 2 CONTAINERS ARE AS FOLLOWS: 1) UB CONTAINER NO SEKU 578937-0 40FT M/S M.NOOMAN ( 1002627) AND 2)UB CONTAINER NO UACU 313023-7 20FT M/S NTA ( 1002244). 3)ASLU-Container No. is charges are pending. | 2025-02-28 | Sharath | High(P1) |  | Closed | 2025-03-18
54 | ACTIVATION OF PORT CONNECT APPLICATION AND CHANGE PREVIOUS MAIL ID-1002310U01 | 2025-03-10 | Sharath | High(P1) |  | Closed | 2025-03-12
55 | Request for storage invoice and stuffing invoice-Stuffing done for WHSU0366887 20' on A/c of All Cargo Logistics(A/c 1002109) | 2025-03-11 | Sharath | High(P1) |  | Closed | 2025-03-18
56 | Updation date not accepting in BTT gate out | 2025-03-12 | Sharath | High(P1) |  | Closed | 2025-03-18
57 | Container details not available in system- | 2025-03-14 | Sharath | High(P1) |  | Closed | 2025-03-18
58 | Stuffing charge invoice reg…DPWU9004420 | 2025-03-14 | Sharath | High(P1) |  | Closed | 2025-03-18
59 | RI not available in CR. | 2025-03-14 | Sharath | High(P1) |  | Closed | 2025-03-18
60 | Port konnect password of Mr.Shyam Sundar (2666) and Mr. Anoop kumar (116828) expired today | 2025-04-01 | Sharath | Medium(P2) |  | Closed | 2025-04-01
61 | Containers are not available in ADO for Cargo-CRSU 147747-9 and CAIU 639430-4 | 2025-03-28 | Sharath | Medium(P2) |  | Closed | 2025-03-28
62 | unable to access CFS module for creating RI- User ID-1005266U01 | 2025-03-27 | Sharath | Medium(P2) |  | Closed | 2025-03-28
63 | User login for Viju sir with Credentials-9055 both in quality and production. | 2025-04-02 | Sharath | High(P1) |  | Closed | 2025-04-10
64 | RI not available in CR | 2025-04-04 | Sharath | High(P1) |  | Closed
65 | TSA number is not reflecting in CFS invoice search screen... | 2025-04-08 | Sharath | High(P1) |  | Closed
66 | Lift on invoice (Empty)-TLLU8663520 (1x40', Empty) of M/s.A A Abdul Azeez (1000646), | 2025-04-07 | Sharath | High(P1) |  | Closed
67 | Issue with Import General Manifest 1128659 dt 19.03.2025 | 2025-04-07 | Sharath | High(P1) |  | Closed | 2025-04-06
68 | De-stuffing (UB) tally recording done for container no.TRHU2336288 (1x20') of M/s. Island Shipping Agencies (1002624 | 2025-04-05 | Sharath | High(P1) |  | Closed | 2025-04-06
69 | Lift off recording done for Cont. no.CAAU8667473 (1x40', Laden) of M/s.M.Nooman (1002627), | 2025-04-05 | Sharath | High(P1) |  | Closed | 2025-04-06
70 | IGM 1129672 dt 25.03.2025 not available in IGM VCN Mapping | 2025-04-05 | Sharath | High(P1) |  | Closed | 2025-04-06
71 | CONTAINER NO CAXU 499504.1 40FT WHICH WAS DESTUFFED IS NOT AVAILABLE IN ADO FOR CARGO. | 2025-04-08 | Sharath | High(P1) |  | Closed | 2025-04-10
72 | JJ SHIPPING ID 1003153 Login issue | 2025-05-06 | Sharath | High(P1) |  | Closed | 2025-05-07
| KKTU 7710054 20FT. LDD- 26.4.2025 LFD- 29.4.2025 LINE NO 21 SUBLINES FROM 1 TO 08. IGM NO 1133044. | 2025-05-06 | Sharath | High(P1) |  | Closed | 2025-05-07
73 | IGM Amendments from POS-NIT- Quixy | 2025-05-07 | Sharath/Manohar | High(P1) |  | Open | 2025-07-09
74 | Issue with Gate In Container WHLU0458479 – Mismatch in Gate Screen/not available in Destfuffing request. | 2025-05-09 | Sharath | Low(P1) |  | Closed | 2025-05-22
75 | Container not available in Tally recording ASLU7084750. | 2025-05-20 | Sharath | High(P1) |  | Closed | 2025-06-05
76 | Manual invoice reg..non availablity of Cntrs in IGM-1137954 | 2025-06-11 | Sharath | High(P1) |  | Closed | 2025-06-13
77 | Cntr details not available in system---IGM 1139244 DT 27.05.2025 | 2025-06-12 | Sharath | High(P1) |  | Closed | 2025-06-19
78 | Error Affecting M/s National Trade & Agencies ( Customs Broker) - Invoice Discrepancy. | 2025-06-12 | Sharath | High(P1) |  | Closed | 2025-06-13
79 | Port konnect customer portal reg-1002109 | 2025-06-16 | Sharath | High(P1) |  | Closed | 2025-06-17
80 | Due to oversight lift on recording was wrongly done laden instead of empty for the container no.BSVU2208058 (20") of M/s Gosree Shipping Agencies (1003083). | 2025-07-02 | Pramod | High(P1) |  | Closed | 2025-07-09
81 | Stuffing charge invoice reg...DPWU9004420 | 2025-07-08 | Shivhar | High(P1) |  | Closed
82 | CONTAINER/LINE/SUBLINE DATA IN ADO POST TALLY DESTUFFING -CARGO MODULE | 2025-07-02 | Sharath | High(P1) |  | Closed | 2025-07-10
83 | Stuffing charge invoice reg...TEMU5817299 | 2025-07-05 | Sharath | High(P1) |  | Closed | 2025-07-08
84 | Cntr details not available in system-IGM1145156 DT 08.07.2025 | 2025-07-21 | Sharath | High(P1) |  | Closed | 2025-07-22 | for business operations it has been processed but need to update on the fix tomorrow-24-07-2025
85 | Issue with Invoice Generation for Completed Transhipment Processes | 2025-07-14 | Sharath | High(P1) |  | In progress | 2025-07-24 | only 2 TSA No.'s are pending
86 | REQUEST TO ENABLE CFS OPTION FOR PORT - ACC NO: 1004705U01 | 2025-07-14 | Sharath | Medium(P2) |  | Closed | 2025-07-14
87 | Container not available in de stuffing request | 2025-07-21 | Sharath | High(P1) |  | Closed | 2025-07-24
88 | The container SEKU5783638 arrived for De stuffing on 25-06-2025. The Mark Enbloc ,capture trailer details and gate in have been updated accordingly. | 2025-07-18 | Sharath | High(P1) |  | In Progress | 2025-07-24