## Sheet1
TaskName | Project | Category | Priority | DueDate | CreateDate | Status
With respect to users does not have PD Account number, other passes are being displayed in the "Duplicate Wharf Entry Pass" list. Please ensure to restricted the same | COPT Support | Bug / Defect | LOW | 2024-06-08 | 2024-08-04 | Closed | 20240804001 | 2024-08-04
Several of our customers have expressed concerns about not receiving SMS/Email alerts for OTP regarding forgotten passwords. | COPT Support | Bug / Defect | LOW | 2024-06-17 | 2024-05-04 | Closed | 20240504001 | 2024-05-04
Noticed certain discrepancies in the "Vessel type" dfined in PortKonnect application. Hence collected the master data from NLP-M in excel format and shared to NIT Team to update the same in the POS application. | COPT Support | Bug / Defect | LOW | 2024-06-17 | 2025-03-03 | Closed | 20241503001 | 2025-03-03
We have encountered several instances in the past where CALINV API messages were not reflected on the NLP-M site. Needs facility to check logs etc to acess the Response from the remote server | COPT Support | Incident | Medium | 2024-06-17 | 2025-10-02 | Closed | 20242202001
Discripancy in Gate-in Gate-out Report, where the gate-in and gate-out times overlaped with the previous gate-in and gate-out times of the same vehicle. | COPT Support | Incident | Medium | 2024-07-27 | 2024-07-02 | Closed | 20240702001
ACKMSG Message - <Message type> node value should be as below:- 6 - if CALINF received well 27 - if CALINF received as error status 1 - if CALINF is cancelled | COPT Support | Incident | Medium | 2024-07-27 | 2026-07-01 | Closed | 20243101001
TPFREP Message - <SaCode> Node value should be the PD Account number of the Shipping Agent as like handled in CALINV & BERALT Message. | COPT Support | Incident | Medium | 2024-07-27 | 2026-07-01 | Closed | 20243101002
Ticket#202401050000006 — Count of Messages | COPT Support | Incident | Medium | 2024-07-27 | 2024-01-02 | Closed | 20240102001
SMS Template :- Requesting the modification of "Cochin Port Trust" to "Cochin Port Authority" in all the SMS messages. | COPT Support | Incident | Medium |  | 2026-05-01 | Closed | 20242901001
Agent change request | COPT Support | Incident | Medium | 11-02-2025 | 2023-02-11 | Closed | 20230211001
Login Issue:- We are not able to access "Wharf Entry Pass" from Login Screen via Firefox browser (Version 118.0.2 (32-bit)). It is working fine with Chrome browser. | COPT Support | Incident | Medium | 2025-01-06 | 2024-05-10 | Closed | 20231710001
VESPRO & CALINV Messages :- At the time when VCN (INCOK123090093) was allocated to the ship EMPRESS (IMO-8716899), its Vessel Profile categorized it as a "Cruise ship." However, we subsequently received an updated VESPRO from GOA Port, which reclassified it as a "Passenger Ship." This alteration had a direct impact on the allocated VCN, causing a shift in the ship's type from "Cruise ship" to "Passenger ship." Consequently, this adjustment affects our billing process, as it denies the customer eligibility for special rates designated for "Cruise ships" and necessitates additional administrative efforts, such as issuing Credit Notes to the customer. Hence, request that the necessary steps be taken to maintain the ship's type as it was at the time of VCN allotment until the final billing process associated with that VCN is completed. | COPT Support | Service Request - Technical | Medium |  | 2025-02-09 | Closed | 20232609001
IGM Related Issues :- 1) Many of the IGM files are not get processed and throws erros at fileprocessing screen. 2) It has come to our attention that despite the IGM file being uploaded into the system , it remains inaccessible for mapping at CFS screen due to Primary key violation (according to Quixy Team, Same Container No appears in multiple line no and subline no in the IGM file. NLP-M Ticket Ref: Ticket#202401120000021). 3) Ensure to update all below variance of IGM files to the system Different values of <MessageId> tag and its meaning is given below: CHPOI03A - On submission of manifest (After allowing IGM No) CHPOI03B - 48 Hrs before the expected time of arrival CHPOI03C - After 1 Hr of grant of entry inward CHPOI03D- Amended IGM | COPT Support | Feature Request | Medium | 2024-07-27 | 2024-09-08 | Closed | 20232108001
Need to schedule Holiday --amendment | COPT Support | Feature Request | Medium | 2024-07-27 | 2025-02-09 | Closed | 20232609001
Disc space in all servers-resolution | COPT Support | Feature Request | Medium | 2024-07-27 | 2025-04-04 | Closed | 20241604001
Assessment of unused space all servers and move to the required servers | COPT Support | Feature Request | Medium | 2024-07-27 | 2025-04-04 | Closed | 20241604002
change of vessel type for INCOK124030087 | COPT Support | Feature Request | Medium | 2024-07-28 | 2024-04-01 | Closed | 20240401001
IGM for LPG/C. NANDA DEVI VOY. ND056 ETA Cochin MULT Berth on 30.03.2024 - 1300 Hrs AGW WP | COPT Support | Feature Request | Medium | 2024-07-29 | 2024-04-02 | Closed | 20240402001
igm quqntity missmatch for incok124030144 | COPT Support | Feature Request | Medium | 2024-07-30 | 2024-04-02 | Closed | 20240402002
ATA update for INCOK12440017 | COPT Support | Feature Request | Medium | 2024-07-31 | 2024-04-05 | Closed | 20240405001
Draft has been updated for INCOK123110146 | COPT Support | Feature Request | Medium | 2024-08-01 | 2024-04-05 | Closed | 20240405002
screenshort wharf entry pass -1.doc | COPT Support | Feature Request | Medium | 2024-08-02 | 2024-04-10 | Closed | 20240410001
RE: IGTPL Data March 2024 | COPT Support | Feature Request | Medium | 2024-08-03 | 2024-04-11 | Closed | 20240411001
RE: Port Users Pass | COPT Support | Feature Request | Medium | 2024-08-04 | 2024-04-12 | Closed | 20240412001
update Clod move for incok120050015 ship 23 | COPT Support | Feature Request | Medium | 2024-08-05 | 2024-04-12 | Closed | 20240412002
RE: VISION-INCOK124040057- Change of Agent. | COPT Support | Performance Issue | Medium | 2024-08-06 | 2024-04-15 | Closed | 20240415001
RE: Fresh water supply-SSL Gujarat | COPT Support | Performance Issue | Medium | 2024-08-07 | 2024-04-15 | Closed | 20240415002
Correction of Towage Charges | COPT Support | Performance Issue | Medium | 2024-08-08 | 2024-04-15 | Closed | 20240415003
Change for GRT | COPT Support | Performance Issue | Medium | 2024-08-09 | 2024-04-15 | Closed | 20240415004
Port Users Pass | COPT Support | Performance Issue | Medium | 2024-08-10 | 2024-04-15 | Closed | 20240415005
Fresh water supply-SSL Gujarat | COPT Support | Technical Support | Medium | 2024-08-11 | 2024-04-15 | Closed | 20240415006
Pcs feil reposting error | COPT Support | Technical Support | Medium | 2024-08-12 | 2024-04-15 | Closed | 20240415007
RE: Correction in shipping bill mapping list - reg | COPT Support | Technical Support | Medium | 2024-08-13 | 2024-04-16 | Closed | 20240416001
Correction in shipping bill mapping list - reg | COPT Support | Technical Support | Medium | 2024-08-14 | 2024-04-16 | Closed | 20240416002
Change the rate in the "Rate column" | COPT Support | UI / UX Feedback | Medium | 2024-08-15 | 2024-04-16 | Closed | 20240416003
changeberth NO. Q1 for vcn incok124040058 | COPT Support | UI / UX Feedback | Medium | 2024-08-16 | 2024-04-16 | Closed | 20240416004
service recording error for incok124020036 Swaran Kalash | COPT Support | UI / UX Feedback | Medium | 2024-08-17 | 2024-04-17 | Closed | 20240417001
RE: SWARNA KALASH INCOK124020036 error showing in service recording | COPT Support | Technical Support | Medium | 2024-08-18 | 2024-04-18 | Closed | 20240418001
RE: INCOK124040099 VALIYAPANI - Error | COPT Support | Technical Support | Medium | 2024-08-19 | 2024-04-19 | Closed | 20240419001
RE: Fresh water supply-Apinya Naree | COPT Support | Technical Support | Medium | 2024-08-20 | 2024-04-19 | Closed | 20240419002
RE: IGM reposting error - reg. | COPT Support | Technical Support | Medium | 2024-08-21 | 2024-04-19 | Closed | 20240419003
Fresh water supply-Apinya Naree | COPT Support | Technical Support | Medium | 2024-08-22 | 2024-04-19 | Closed | 20240419006
RE: Container Vessels Teu Capacity | COPT Support | Technical Support | Medium | 2024-08-23 | 2024-04-22 | Closed | 20240422001
vcn 040097 Dawn Mannsarovar shiffiting pilot name repeated | COPT Support | Technical Support | Medium | 2024-08-24 | 2024-04-22 | Closed | 20240422002
RE: Add new Pilots Name in PortKonnect - reg | COPT Support | Technical Support | Medium | 2024-08-25 | 2024-04-23 | Closed | 20240423001
RE: NANDA DEVI-INCOK124040023 | COPT Support | Technical Support | Medium | 2024-08-26 | 2024-04-23 | Closed | 20240423002
update vcn NO for BRGCP2400001 shun 1 | COPT Support | Technical Support | Medium | 2024-08-27 | 2024-04-23 | Closed | 20240423003
sailling requst verification error | COPT Support | Technical Support | Medium | 2024-08-28 | 2024-04-23 | Closed | 20240423004
RE: Correction in Draft Survey Records - reg. | COPT Support | Technical Support | Medium | 2024-08-29 | 2024-04-24 | Closed | 20240424001
RE: Change GRT | COPT Support | Technical Support | Medium | 2024-08-30 | 2024-04-24 | Closed | 20240424002
RE: INCOK124040133 MSC ARCHIMIDIS - MAINLINE VESSEL | COPT Support | Bug / Defect | Medium | 2024-08-31 | 2024-04-24 | Closed | 20240424003
RE: change of Agent. APINYA NAREE-INCOK124040104 | COPT Support | Bug / Defect | Medium | 2024-09-01 | 2024-04-24 | Closed | 20240424004
RE: Ticket#202403140000046 — Master data synchronization - "Vessel type" and "Port of Registry" | COPT Support | Bug / Defect | Medium | 2024-09-02 | 2024-04-24 | Closed | 20240424005
Change GRT | COPT Support | Bug / Defect | Medium | 2024-09-03 | 2024-04-24 | Closed | 20240424006
INCOK124040133 MSC ARCHIMIDIS - MAINLINE VESSEL | COPT Support | Bug / Defect | Medium | 2024-09-04 | 2024-04-24 | Closed | 20240424007
Financial Analysis report not working | COPT Support | Bug / Defect | Medium | 2024-09-05 | 2024-04-24 | Closed | 20240424008
RE: valid_to date - Extension | COPT Support | Bug / Defect | Medium | 2024-09-06 | 2024-04-30 | Closed | 20240430001
Vcn 24040073 Swarna Pushp not showing in shipping program | COPT Support | Bug / Defect | Medium | 2024-09-07 | 2024-04-30 | Closed | 20240430002
Sailing request not showing in shipping progarm screen-VCN040161 SERENADE OF THE SEAS | COPT Support | Bug / Defect | Medium | 2024-09-08 | 2024-05-02 | Closed | 20240502001
BERTHING request not showing in shipping progarm screen-VCN040137 WAN HAI 515 | COPT Support | Bug / Defect | Medium | 2024-09-09 | 2024-05-02 | Closed | 20240502002
User unable save the temporary gate pass (save button is disable) | COPT Support | Bug / Defect | Medium | 2024-09-10 | 2024-05-02 | Closed | 20240502003
Issue on repost IGM | COPT Support | Bug / Defect | Medium | 2024-09-11 | 2024-05-02 | Closed | 20240502004
As per SOR composite package applicable for this vessel.Please note that this vessel built from Private Jetty Cochin and sailout as Foreign,So please remove the inward pilotage in this Estimation Invoice. | COPT Support | Bug / Defect | Medium | 2024-09-12 | 2024-05-02 | Closed | 20240502005
while reposting the IGM for the following vessel through PCS Files Processing getting error message is in seen | COPT Support | Bug / Defect | Medium | 2024-09-13 | 2024-05-02 | Closed | 20240502006
Please update pull back end time for 22:45 | COPT Support | Bug / Defect | Medium | 2024-09-14 | 2024-05-02 | Closed | 20240502007
SERENADE OF THE SEAS-INCOK124040161 - Marine Invoice Incorrect | COPT Support | Bug / Defect | Medium | 2024-09-15 | 2024-05-02 | Closed | 20240502008
INCOK124040156 CELESTE - total amount(315604.7 ),Please correct total amount. | COPT Support | Bug / Defect | Medium | 2024-09-16 | 2024-05-03 | Closed | 20240503001
Please update vessel type Cruise Ship instead of Passenger ship | COPT Support | Bug / Defect | Medium | 2024-09-17 | 2024-05-03 | Closed | 20240503002
Please check berth name Q8 to DG | COPT Support | Bug / Defect | Medium | 2024-09-18 | 2024-05-03 | Closed | 20240503003
Please remove repeated pilot name | COPT Support | Bug / Defect | Medium | 2024-09-19 | 2024-05-03 | Closed | 20240503004
SAN PRIDE - INCOK122070087 - Marine Invoice Error. | COPT Support | Bug / Defect | Medium | 2024-09-20 | 2024-05-06 | Closed | 20240506001
Marine Invoice Pending - SM KAVERI-INCOK124050022 | COPT Support | Bug / Defect | Medium | 2024-09-21 | 2024-05-06 | Closed | 20240506002
IGTPL Data April 2024 | COPT Support | Bug / Defect | Medium | 2024-09-22 | 2024-05-06 | Closed | 20240506003
The "Forgot Password" option is currently not functioning properly | COPT Support | Bug / Defect | Medium | 2024-09-23 | 2024-05-07 | Closed | 20240507001
A humble request to kindly change vessel type as Cruise for MV.INSIGNIA and MV.RIVIERA | COPT Support | Bug / Defect | Medium | 2024-09-24 | 2024-05-07 | Closed | 20240507002
upload attached IGTPL Data ( Voyage, Traffic & Invoice) for the month of April 2024 | COPT Support | Bug / Defect | Medium | 2024-09-25 | 2024-05-08 | Closed | 20240508001
Change of Agent. | COPT Support | Bug / Defect | Medium | 2024-09-26 | 2024-05-08 | Closed | 20240508002
E-invoice Error Status in Portkonnect | COPT Support | Bug / Defect | Medium | 2024-09-27 | 2024-05-09 | Closed | 20240509001
Financial Analysis report not working | COPT Support | Bug / Defect | Medium | 2024-09-28 | 2024-05-09 | Closed | 20240509002
Marine Invoice error - SM KAVERI-INCOK124050022 | COPT Support | Bug / Defect | Medium | 2024-09-29 | 2024-05-10 | Closed | 20240510001
IGM not listed - MT STELLAR BEVERLY ( VCN : INCOK124050052, IMO No. 9208069 ) | COPT Support | Bug / Defect | Medium | 2024-09-30 | 2024-05-13 | Closed | 20240513001
SAN PRIDE - INCOK122070087 - Marine Invoice Error. | COPT Support | Bug / Defect | Medium | 2024-10-01 | 2024-05-14 | Closed | 20240514001
Please reset the password of user-id :9055 | COPT Support | Bug / Defect | Medium | 2024-10-02 | 2024-05-15 | Closed | 20240515001
VAILANKANNI II-BRGCP2000003 | COPT Support | Bug / Defect | Medium | 2024-10-03 | 2024-05-15 | Closed | 20240515002
INCOK124040156 CELESTE -Final marine Invoice | COPT Support | Bug / Defect | Medium | 2024-10-04 | 2024-05-15 | Closed | 20240515003
Berth CSLQ3 - Composite package charge - reg. | COPT Support | Bug / Defect | Medium | 2024-10-05 | 2024-05-16 | Closed | 20240516001
IGM not listed - M.T.ORIENTAL GERBERA ( VCN :INCOK124050045 , IMO No. 9924716 ) | COPT Support | Bug / Defect | Medium | 2024-10-06 | 2024-05-16 | Closed | 20240516002
Change vessel type - Voyage | COPT Support | Bug / Defect | Medium | 2024-10-07 | 2024-05-16 | Closed | 20240516003
Fields to be extracted from Portkonnect for printing Port Users Pass | COPT Support | Bug / Defect | Medium | 2024-10-08 | 2024-05-17 | Closed | 20240517001
RE: IGM VCN mapping reg...igm 2374715 dated 20.04.2024 and 2374794 dated 22.04.2024...2376221 dt 07.05.2024 | COPT Support | Bug / Defect | Medium | 2024-10-09 | 2024-05-18 | Closed | 20240518001
SERENADE OF THE SEAS-INCOK124040161 - Marine Invoice Incorrect. | COPT Support | Bug / Defect | Medium | 2024-10-10 | 2024-05-20 | Closed | 20240520001
VAILANKANNI II-BRGCP2000003 | COPT Support | Bug / Defect | Medium | 2024-10-11 | 2024-05-21 | Closed | 20240521001
Fields to be extracted from PortKonnect for printing Port Users Pass | COPT Support | Bug / Defect | Medium | 2024-10-12 | 2024-05-22 | Closed | 20240522001
Portkonnect SAP Status Issue-rreg. | COPT Support | Bug / Defect | Medium | 2024-10-13 | 2024-05-22 | Closed | 20240522002
INCOK124050102 WAN HAI 501 Main Line - vessel. | COPT Support | Bug / Defect | Medium | 2024-10-14 | 2024-05-27 | Closed | 20240527001
Vessel not available for Voyage Registration screen | COPT Support | Bug / Defect | Medium | 2024-10-15 | 2024-05-27 | Closed | 20240527002
Duplicate Vehicles scanned for Gate in | COPT Support | Bug / Defect | Medium | 2024-10-16 | 2024-05-29 | Closed | 20240529001
IDLING BERTH HIRE CHARGES | COPT Support | Bug / Defect | Medium | 2024-10-17 | 2024-05-30 | Closed | 20240530001
BEYPORE SULTAN - 9711664 Not available for Voyage Registration - URGENT!! | COPT Support | Bug / Defect | Medium | 2024-10-18 | 2024-05-31 | Closed | 20240531001
Ticket#202405310000039 — <TypeOfCargo>xx</TypeOfCargo> node value Reg | COPT Support | Bug / Defect | Medium | 2024-10-19 | 2024-05-31 | Closed | 20240531002
IGM is not available in IGM VCN screen | COPT Support | Bug / Defect | Medium | 2024-10-20 | 2024-05-31 | Closed | 20240531003
EXport storage invoice for RI74320 missing | COPT Support | Bug / Defect | Medium | 2024-10-21 | 2024-05-31 | Closed | 20240531004
Ramp Examption MSNU3049339 | COPT Support | Bug / Defect | Medium | 2024-10-22 | 2024-06-03 | Closed | 20240603001
Ramp Examption MEDU6105526 | COPT Support | Bug / Defect | Medium | 2024-10-23 | 2024-06-03 | Closed | 20240603002
Lift on Charges missing | COPT Support | Bug / Defect | Medium | 2024-10-24 | 2024-06-03 | Closed | 20240603003
Import charges Destuffing CAIU7950455 | COPT Support | Bug / Defect | Medium | 2024-10-25 | 2024-06-03 | Closed | 20240603004
Change of Agent- MV SRI ANJANA-INCOK121120131 | COPT Support | Bug / Defect | Medium | 2024-10-26 | 2024-06-04 | Closed | 20240604001
IGM details are not being reflected in the IGM listing. | COPT Support | Bug / Defect | Medium | 2024-10-27 | 2024-06-05 | Closed | 20240605001
RE: VCN INCOK124050162 - ATA OCEAN - for vcn cacellation. | COPT Support | Bug / Defect | Medium | 2024-10-28 | 2024-06-05 | Closed | 20240605002
Deletion of Fresh water charge for COINGF24ST05660 | COPT Support | Bug / Defect | Medium | 2024-10-29 | 2024-06-06 | Closed | 20240606001
VCN050133 OCEAN FAYE shifting update in Shipping program | COPT Support | Bug / Defect | Hign | 2024-10-30 | 2024-06-06 | Closed | 20240606002
User login issue | COPT Support | Bug / Defect | Hign | 2024-10-31 | 2024-06-06 | Closed | 20240606003
Interim invoice | COPT Support | Bug / Defect | Hign | 2024-11-01 | 2024-06-06 | Closed | 20240606004
XIN LIAN YUN GANG - vcn request in voyage registion - PortKonnect | COPT Support | Bug / Defect | Hign | 2024-11-02 | 2024-06-07 | Closed | 20240607001
Kindly change the commodity code for the vessel INCOK124050153 | COPT Support | Bug / Defect | Hign | 2024-11-03 | 2024-06-07 | Closed | 20240607002
VCN050133 OCEAN FAYE sailing update in Shipping program | COPT Support | Bug / Defect | Hign | 2024-11-04 | 2024-06-07 | Closed | 20240607003
same truck is coming up once scanning is done at Cochin Port Authority Ekm Wharf In-Gate. | COPT Support | Bug / Defect | Hign | 2024-11-05 | 2024-06-07 | Closed | 20240607004
THINNAKARA-INCOK123080064 | COPT Support | Bug / Defect | Hign | 2024-11-06 | 2024-06-10 | Closed | 20240610001
LPG Handling at MULT by IOCL | COPT Support | Bug / Defect | Hign | 2024-11-07 | 2024-06-10 | Closed | 20240610002
Requested to change ATA for INCOK124060002 | COPT Support | Bug / Defect | Hign | 2024-11-08 | 2024-06-10 | Closed | 20240610003
Storage Invoice | COPT Support | Bug / Defect | Hign | 2024-11-09 | 2024-06-10 | Closed | 20240610004
In Service Recording Screen verification showing "ERROR" for VCN INCOKI 2405139 ROSE GAS | COPT Support | Bug / Defect | Hign | 2024-11-10 | 2024-06-11 | Closed | 20240611001
BUNKER REQUEST CANCELLATION LETTER - ATA OCEAN [INCOK124050162] | COPT Support | Bug / Defect | Hign | 2024-11-11 | 2024-06-12 | Closed | 20240612001
Wrong mapping of SB to RI- Deletion of SB | COPT Support | Bug / Defect | Hign | 2024-11-12 | 2024-06-18 | Closed | 20240618001
Requestet to change GRT for INS VIKRANT | COPT Support | Bug / Defect | Hign | 2024-11-13 | 2024-06-18 | Closed | 20240618002
New Agent-OZONE CARGO | COPT Support | Bug / Defect | Hign | 2024-11-14 | 2024-06-19 | Closed | 20240619001
IGM not listed for MT SUNNY MARK (INCOK124060068) | COPT Support | Bug / Defect | Hign | 2024-11-15 | 2024-06-20 | Closed | 20240620001
Correction option in Capture Arrival/ Departure | COPT Support | Bug / Defect | Hign | 2024-11-16 | 2024-06-20 | Closed | 20240620002
SLAB has been added for shifting (LAKSHADWEEP SEA-INCOK123120002) | COPT Support | Bug / Defect | Hign | 2024-11-17 | 2024-06-20 | Closed | 20240620003
Not able to process Voyage Registration file - CALINF : 9512202 | COPT Support | Bug / Defect | Hign | 2024-11-18 | 2024-06-21 | Closed | 20240621001
DISCREPANCY IN SHIFTING CHARGE - HSC. CHERIYAPANI-INCOK124050112 - | COPT Support | Bug / Defect | Hign | 2024-11-19 | 2024-06-24 | Closed | 20240624001
SRI ANJANA-INCOK121120131- CHANGE OF AGENT | COPT Support | Bug / Defect | Hign | 2024-11-20 | 2024-06-24 | Closed | 20240624002
Gang Demanded and Allocated wrongly for Gang Plan | COPT Support | Bug / Defect | Hign | 2024-11-21 | 2024-06-25 | Closed | 20240625001
Berman' failed status -16.06.2024 to 26.06.2024) | COPT Support | Bug / Defect | Hign | 2024-11-22 | 2024-06-25 | Closed | 20240625002
Change GRT for INS VIKRANT | COPT Support | Bug / Defect | Hign | 2024-11-23 | 2024-06-28 | Closed | 20240628001
RE: Multiple records for the same truck | COPT Support | Bug / Defect | Hign | 2024-11-24 | 2024-07-01 | Closed | 20240701001
Shifting to CSL Repair dock on 23.06.2024 for VCN 23040095 IND SUJATHA | COPT Support | Bug / Defect | Hign | 2024-11-25 | 2024-07-02 | Closed | 20240702001
Upload IGM List for VCN 23040095 IND SUJATHA | COPT Support | Bug / Defect | Hign | 2024-11-26 | 2024-07-02 | Closed | 20240702002
Request for changing Agent Name | COPT Support | Bug / Defect | Hign | 2024-11-27 | 2024-07-03 | Closed | 20240703001
Boat crew Pass issue | COPT Support | Bug / Defect | Hign | 2024-11-28 | 2024-07-05 | Closed | 20240705001
RE: THINNAKARA-INCOK123080064 | COPT Support | Bug / Defect | Hign | 2024-11-29 | 2024-07-08 | Closed | 20240708001
RE: Voyage Registration file handling issue. | COPT Support | Bug / Defect | Hign | 2024-11-30 | 2024-07-08 | Closed | 20240708002
RE: Validating the status of ICGS Vessels to Parked - reg. | COPT Support | Bug / Defect | Hign | 2024-12-01 | 2024-07-09 | Closed | 20240709001
Pre Berthing delay reason wrongly marked NON AVAILABILITY OF BERTH for VCN 24070003 WAN HAI 501 | COPT Support | Bug / Defect | Hign | 2024-12-02 | 2024-07-10 | Closed | 20240710001
RE: Diversion of MT Pagos - release of parked amount | COPT Support | Bug / Defect | Hign | 2024-12-03 | 2024-07-12 | Closed | 20240712001
RE: Fields to be extracted from PortKonnect for printing Port Users Pass | COPT Support | Bug / Defect | Hign | 2024-12-04 | 2024-07-12 | Closed | 20240712002
Requested to change Pilot cancellation date for JAG PAVITRA INCOK124070056 | COPT Support | Bug / Defect | Hign | 2024-12-05 | 2024-07-16 | Closed | 20240716001
Shifting showing error for VCN 24070047 ICGS SAMARTH | COPT Support | Bug / Defect | Hign | 2024-12-06 | 2024-07-16 | Closed | 20240716002
RE: Multiple records for the same truck FOR KL27D9087 | COPT Support | Bug / Defect | Hign | 2024-12-07 | 2024-07-19 | Closed | 20240719001
Fields to be extracted from PortKonnect for printing Port Users Pass | COPT Support | Bug / Defect | Hign | 2024-12-08 | 2024-07-19 | Closed | 20240719002
RE: Tank Farm Details | COPT Support | Bug / Defect | Hign | 2024-12-09 | 2024-07-22 | Closed | 20240722001
Re: PAYSTS - Node value width Error. | COPT Support | Bug / Defect | Hign | 2024-12-10 | 2024-07-25 | Closed | 20240725001
M.V MOGRAL V.0083W - BUNKER REQUEST TECHNICAL ERROR | COPT Support | Bug / Defect | Hign | 2024-12-11 | 2024-07-26 | Closed | 20240726001
RE: MV APJ JAI AT COCHIN | COPT Support | Bug / Defect | Hign | 2024-12-12 | 2024-07-26 | Closed | 20240726002
GST EXEMPTED FOR DP ACCOUNT No.1004941 | COPT Support | Bug / Defect | Hign | 2024-12-13 | 2024-07-30 | Closed | 20240730001
RE: VCN Cancellation for INCOK124070111 BASHUNDHARA LPG CHALLENGE | COPT Support | Bug / Defect | Hign | 2024-12-14 | 2024-07-30 | Closed | 20240730002
RE: Weekly Pass not showing up in users login ID screen | COPT Support | Bug / Defect | Hign | 2024-12-15 | 2024-07-30 | Closed | 20240730003
RE: INCOK124070111 BASHUNDHARA LPG CHALLENGE - Remove SGST & CGST. | COPT Support | Bug / Defect | Hign | 2024-12-16 | 2024-07-31 | Closed | 20240731001
PAYSTS - Folder | COPT Support | Bug / Defect | Hign | 2024-12-17 | 2024-07-31 | Closed | 20240731002
Pilot Cancellation - Reg | COPT Support | Bug / Defect | Critical | 2024-12-18 | 2024-07-31 | Closed | 20240731003
RE: TPFREP Message Final Format. | COPT Support | Bug / Defect | Critical | 2024-12-19 | 2024-08-01 | Closed | 20240801001
RE: Pilot Cancellation - Error | COPT Support | Bug / Defect | Critical | 2024-12-20 | 2024-08-07 | Closed | 20240807001
Requested to upload IGTPL Data (Voyage, Traffic & Invoice) for the month of July 2024 | COPT Support | Bug / Defect | Critical | 2024-12-21 | 2024-08-08 | Closed | 20240808001
RE: TPFREP message wrt Liquid Bulk (MARVELS-INCOK124080002, IMO: 9317078) | COPT Support | Bug / Defect | Critical | 2024-12-22 | 2024-08-09 | Closed | 20240809001
LDCL A/c No wrongly mark 1002213 pl change to 1002214 for VCN 24080041 LAGOONS | COPT Support | Bug / Defect | Critical | 2024-12-23 | 2024-08-09 | Closed | 20240809002
Request for Online berthing document | COPT Support | Bug / Defect | Critical | 2024-12-24 | 2024-08-09 | Closed | 20240809003
RE: BERMAN not available at Marine Request screen | COPT Support | Bug / Defect | Critical | 2024-12-25 | 2024-08-12 | Closed | 20240812001
RE: VRC SPLITED TO DIFFERENT AGENT. | COPT Support | Bug / Defect | Critical | 2024-12-26 | 2024-08-12 | Closed | 20240812002
RE: Agent name change for Vessel INS SUJATA on 11-08-2024. | COPT Support | Bug / Defect | Critical | 2024-12-27 | 2024-08-14 | Closed | 20240814001
RE: Change of Agent. SRI ANJANA-INCOK121120131 | COPT Support | Bug / Defect | Critical | 2024-12-28 | 2024-08-19 | Closed | 20240819001
Pilot Detention - Delete from Marine Invoice | COPT Support | Bug / Defect | Critical | 2024-12-29 | 2024-08-19 | Closed | 20240819002
MAISHA-INCOK124080015 | COPT Support | Bug / Defect | Critical | 2024-12-30 | 2024-08-19 | Closed | 20240819003
Requested for email notification( port entry & clearence certicate) trigger in Voyage registration for the agents. | COPT Support | Bug / Defect | Critical | 2024-12-31 | 2024-08-20 | Closed | 20240820001
AS Alexandria - VCN Number correction | COPT Support | Bug / Defect | Critical | 2025-01-01 | 2024-08-21 | Closed | 20240821001
PORTKONNECT SAP STATUS ISSUE | COPT Support | Bug / Defect | Critical | 2025-01-02 | 2024-08-21 | Closed | 20240821002
Re: shipping program screen - only active pilots to be displayed | COPT Support | Bug / Defect | Critical | 2025-01-03 | 2024-08-22 | Closed | 20240822001
RE: Deletion of bunkering invoices | COPT Support | Bug / Defect | Critical | 2025-01-04 | 2024-08-22 | Closed | 20240822002
RE: DAWN MANSAROVAR ATA Correction | COPT Support | Bug / Defect | Critical | 2025-01-05 | 2024-08-22 | Closed | 20240822003
RE: M.T SANMAR SONNET -DOUBLE ENTRY | COPT Support | Bug / Defect | Critical | 2025-01-06 | 2024-08-23 | Closed | 20240823001
GST EXEMPTED FOR DP ACCOUNT No.1004941 (IOCL-SEZ costumer). - MULT VESSELS. | COPT Support | Bug / Defect | Critical | 2025-01-07 | 2024-08-23 | Closed | 20240823002
BERMAN submission via POS should be blocked | COPT Support | Bug / Defect | Critical | 2025-01-08 | 2024-08-23 | Closed | 20240823003
Purpose of Vist - Master Data. | COPT Support | Bug / Defect | Critical | 2025-01-09 | 2024-08-27 | Closed | 20240827001
RE: Pre-Berthing Delay/Detention details - LOV modification Reg. | COPT Support | Bug / Defect | Critical | 2025-01-10 | 2024-08-28 | Closed | 20240828001
RE: Detension Charges -Remove for Vcn INCOK124080122 SSL MUMBAI & TCI EXPRESS-INCOK124080126. | COPT Support | Bug / Defect | Critical | 2025-01-11 | 2024-09-02 | Closed | 20240902001
RE: PortKonnect issue-fresh water charges | COPT Support | Bug / Defect | Critical | 2025-01-12 | 2024-09-03 | Closed | 20240903001
Shifting charges for IOC from Mult berth | COPT Support | Bug / Defect | Critical | 2025-01-13 | #VALUE! | Closed
RE: Multiple records for the same truck | COPT Support | Bug / Defect | Critical | 2025-01-14 | 2024-09-03 | Closed | 20240903002
RE: PortKonnect issue-fresh water charges | COPT Support | Bug / Defect | Critical | 2025-01-15 | 2024-09-03 | Closed | 20240903003
RE: Detension Charges -Remove | COPT Support | Bug / Defect | Critical | 2025-01-16 | 2024-09-03 | Closed | 20240903004
RE: CHANGE OF AGENT. | COPT Support | Bug / Defect | Critical | 2025-01-17 | 2024-09-04 | Closed | 20240904001
RE: Update In Printout Format In Bunkering Module | COPT Support | Bug / Defect | Critical | 2025-01-18 | 2024-09-04 | Closed | 20240904002
Re: Validation issues with CALINF - Already voyage number existed for this Vessel CARGO operations need to check and need some clarifications from COPA | COPT Support | Bug / Defect | Critical | 2025-01-19 | 2024-09-06 | Closed | 20240906001
RE: IGM listing error - reg. | COPT Support | Bug / Defect | Critical | 2025-01-20 | 2024-09-09 | Closed | 20240909001
RE: Abbreviation of Inv. No. in Portkonnect | COPT Support | Bug / Defect | Critical | 2025-01-21 | 2024-09-13 | Closed | 20240913001
Re: EMPRESS-INCOK124090036 - Estimation & Invoice - Cruise vessel | COPT Support | Bug / Defect | Critical | 2025-01-22 | 2024-08-25 | Closed | 20240825001
RE: Certificate of Clearence | COPT Support | Bug / Defect | Critical | 2025-01-23 | 2024-09-13 | Closed | 20240913002
RE: GST EXEMPTED FOR DP ACCOUNT No.1004941 (IOCL-B2C). - MULT VESSELS - BW BIRCH-INCOK124090020 DT 19.09.24 | COPT Support | Bug / Defect | Critical | 2025-01-24 | 2024-09-19 | Closed | 20240919001
RE: Change GRT to 58590-reg | COPT Support | Bug / Defect | Critical | 2025-01-25 | 2024-09-20 | Closed | 20240920001
RE: IGM List error - reg. | COPT Support | Bug / Defect | Critical | 2025-01-26 | 2024-09-20 | Closed | 20240920002
RE: GST EXEMPTED FOR DP ACCOUNT No.1004941 (IOCL-SEZ costumer). - MULT VESSELS. | COPT Support | Bug / Defect | Critical | 2025-01-27 | 2024-09-24 | Closed | 20240924001
RE: Change rate of shifting charges-reg | COPT Support | Bug / Defect | Critical | 2025-01-28 | 2024-09-25 | Closed | 20240925001
Regarding ATA Change functionality. | COPT Support | Bug / Defect | Critical | 2025-01-29 | 2024-09-26 | Closed | 20240926001
RE: Multiple records for the same truck | COPT Support | Bug / Defect | Critical | 2025-01-30 | 2024-10-01 | Closed | 20241001001
RE: PBD_Reasons | COPT Support | Bug / Defect | Critical | 2025-01-31 | 2024-10-04 | Closed | 20241004001
RE: IGTPL Data Sep. 2024 | COPT Support | Bug / Defect | Critical | 2025-02-01 | 2024-10-04 | Closed | 20241004002
RE: Update In Printout Format In Bunkering Module | COPT Support | Bug / Defect | Critical | 2025-02-02 | 2024-10-04 | Closed | 20241004003
Invoices not generated after tally recorded in system. | COPT Support | Bug / Defect | Critical | 2025-02-03 | 2024-10-04 | Closed | 20241004004
Option to open the "entry of anchorage" till vessels sail out | COPT Support | Bug / Defect | Critical | 2025-02-04 | 2024-10-04 | Closed | 20241004004
Non-Availability of IGMs | COPT Support | Bug / Defect | Critical | 2025-02-05 | 2024-10-07 | Closed | 20241007001
Change shifting charges. | COPT Support | Bug / Defect | Critical | 2025-02-06 | 2024-10-07 | Closed | 20241007002
Re: PBD_Reasons | COPT Support | Bug / Defect | Critical | 2025-02-07 | 2024-10-07 | Closed | 20241007003
Change in reason for visit - reg. | COPT Support | Bug / Defect | Critical | 2025-02-08 | 2024-10-08 | Closed | 20241008001
RE: Cancellation of bunkering estimation invoice for INCOK124090114 | COPT Support | Bug / Defect | Critical | 2025-02-09 | 2024-10-09 | Closed | 20241009001
Re: Certificate of Entry & Clearance | COPT Support | Bug / Defect | Critical | 2025-02-10 | 2024-10-10 | Closed | 20241010001
Cancellation of bunkering estimation invoice for COINGE24ST02457 | COPT Support | Bug / Defect | Critical | 2025-02-11 | 2024-10-11 | Closed | 20241011001
Bunkering Permission Cancellation Request MV.X-PRESS KAVERI VOY.24027 at Cochin Anchorage on 11.10.2024 | COPT Support | Bug / Defect | Critical | 2025-02-12 | 2024-10-15 | Closed | 20241015001
RE: SAGAR TARA-INCOK124080070 -Discrepancy in Marine invoice-Incorrect berthing date | COPT Support | Bug / Defect | Critical | 2025-02-13 | 2024-10-15 | Closed | 20241015002
RE: Estimation correction - INCOK124100104 ALMI NAVIGATOR - reg | COPT Support | Bug / Defect | Critical | 2025-02-14 | 2024-10-21 | Closed | 20241021001
RE: VCN CANCELLATION / MT CHEMROAD SEA INCOK124100112 | COPT Support | Bug / Defect | Critical | 2025-02-15 | 2024-10-28 | Closed | 20241028001
RE: SRI ANJANA-INCOK121120131- CHANGE OF AGENT | COPT Support | Bug / Defect | Critical | 2025-02-16 | 2024-10-28 | Closed | 20241028002
RE: Not able to access notification. | COPT Support | Bug / Defect | Critical | 2025-02-17 | 2024-10-29 | Closed | 20241029001
RE: VCN CANCELLATION / MT CHEMROAD SEA INCOK124100112 | COPT Support | Bug / Defect | Critical | 2025-02-18 | 2024-10-29 | Closed | 20241029002
MV. SOMNATH-INCOK124100117- 25.10.24 -- Invoice generation issue | COPT Support | Bug / Defect | Critical | 2025-02-19 | 2024-11-01 | Closed | 20241101001
Correction in export application quantity - reg | COPT Support | Bug / Defect | Critical | 2025-02-20 | 2024-11-01 | Closed | 20241101002
Re: Discrepancies in the Financial Analysis Report - reg. | COPT Support | Bug / Defect | Critical | 2025-02-21 | 2024-11-01 | Closed | 20241101003
RE: SMS Issue - Gate Entry Pass. | COPT Support | Bug / Defect | Critical | 2025-02-22 | 2024-11-04 | Closed | 20241104001
RE: QR Code gate out issue for KL43D9789 & KL46X5825 | COPT Support | Bug / Defect | Critical | 2025-02-23 | 2024-11-04 | Closed | 20241104002
Cancellation of estimation invoice of M.V. SCI CHENNAI V 2412 | COPT Support | Bug / Defect | Critical | 2025-02-24 | 2024-11-05 | Closed | 20241105001
RE: IGTPL Data October 2024 | COPT Support | Bug / Defect | Critical | 2025-02-25 | 2024-11-05 | Closed | 20241105002
RE: Certificate of Entry & Clearance | COPT Support | Bug / Defect | Critical | 2025-02-26 | 2024-11-06 | Closed | 20241106001
RE: User type change - Request | COPT Support | Bug / Defect | Critical | 2025-02-27 | 2024-11-07 | Closed | 20241107001
RE: Issue uploading VCN number | COPT Support | Bug / Defect | Critical | 2025-02-28 | 2024-11-07 | Closed | 20241107002
RE: Records meant for printing Port Users Pass | COPT Support | Bug / Defect | Critical | 2025-03-01 | 2024-11-08 | Closed | 20241108001
PD account change in respect of M/s WINSTAR SHIPPING SERVICES. | COPT Support | Bug / Defect | Critical | 2025-03-02 | 2024-11-08 | Closed | 20241108002
Service Recording - Tug Services - Pullback start date and end date - recording | COPT Support | Bug / Defect | Critical | 2025-03-03 | 2024-11-11 | Closed | 20241111001
RE: Cancellation of estimation invoice of M.V. SCI CHENNAI V 2412 | COPT Support | Bug / Defect | Critical | 2025-03-04 | 2024-11-12 | Closed | 20241112001
Fwd: [TKT20241101-12923] Technician Commented : CALINF xml files without mandatory field "Type of Cargo". | COPT Support | Bug / Defect | Critical | 2025-03-05 | 2024-11-12 | Closed | 20241112002
RE: CANCELLATION LETTER OF THE VESSEL MV/MT MEGHNA STAR SB,NO.5390832 DT.06.11.2024 | COPT Support | Bug / Defect | Critical | 2025-03-06 | 2024-11-14 | Closed | 20241114001
RE: Correction in IGM and invoices - reg | COPT Support | Bug / Defect | Critical | 2025-03-07 | 2024-11-15 | Closed | 20241115001
RE: CANCELLATION LETTER OF THE VESSEL MV/MT ANTHEM OF THE SEAS SB,NO. 5556240 DT.13.11.2024 | COPT Support | Bug / Defect | Critical | 2025-03-08 | 2024-11-19 | Closed | 20241119001
RE: Shipping movement report not working | COPT Support | Bug / Defect | Critical | 2025-03-09 | 2024-11-19 | Closed | 20241119002
RE: Enabling draft survery recording - reg | COPT Support | Bug / Defect | Critical | 2025-03-10 | 2024-11-20 | Closed | 20241120001
RE: Gate Out Time Updation - KL39T8542 | COPT Support | Bug / Defect | Critical | 2025-03-11 | 2024-11-21 | Closed | 20241121001
RE: Validating the status of INS VIKRAMADITYA to Parked - reg. | COPT Support | Bug / Defect | Critical | 2025-03-12 | 2024-11-21 | Closed | 20241121002
RE: Change in Reason for visit - reg | COPT Support | Bug / Defect | Critical | 2025-03-13 | 2024-11-22 | Closed | 20241122001
RE: Error KODITHALA-INCOK124050134 | COPT Support | Bug / Defect | Critical | 2025-03-14 | 2024-11-26 | Closed | 20241126001
RE: CALINF xml files without mandatory field "Type of Cargo". | COPT Support | Bug / Defect | Critical | 2025-03-15 | 2024-11-27 | Closed | 20241127001
RE: Incorrect Fresh water Quantity. | COPT Support | Bug / Defect | Critical | 2025-03-16 | 2024-11-27 | Closed | 20241127002
Entry & Clearance certificate | COPT Support | Bug / Defect | Critical | 2025-03-17 | 2024-11-27 | Closed | 20241127003
RE: Error | COPT Support | Bug / Defect | Critical | 2025-03-18 | 2024-11-28 | Closed | 20241128001
Workflow Approval Issue | COPT Support | Bug / Defect | Critical | 2025-03-19 | 2024-11-28 | Closed | 20241128002
RE: Correction in invoices - reg. | COPT Support | Bug / Defect | Critical | 2025-03-20 | 2024-11-28 | Closed | 20241128003
Voyage Registration - Actions > View not functioning | COPT Support | Bug / Defect | Critical | 2025-03-21 | 2024-12-03 | Closed | 20241203001
For increase the decimal places in the 'Rate' field of Offline Screen | COPT Support | Bug / Defect | Critical | 2025-03-22 | 2024-12-03 | Closed | 20241203003
Re: Invoices not reflected in Port Konnect report ( Financial anylysis report) Mapping of GL codes. | COPT Support | Bug / Defect | Critical | 23-06-2025 | 2024-12-03 | Closed | 20241203004
Re: SAP Portkonnect Status Issue-reg. | COPT Support | Bug / Defect | Critical | 23-06-2026 | 2024-12-16 | Closed | 20241216001
Re: Request for assistance in Recovering Steamer Register Invoice Report (Data). | COPT Support | Bug / Defect | Critical | 2025-01-23 | 2025-01-06 | Closed | 20241237001
share of vessels with the sizes compatible with maximum draft[Audit Data] | COPT Support | Bug / Defect | Critical | 2025-01-24 | 2025-01-15 | Closed | 20250115001
Re: ISSUE IN TEMPORARY WHARF ENTRY PASS PENDING LIST DISPLAY | COPT Support | Bug / Defect | Critical | 2025-01-15 | 2025-01-15 | Closed | 20250115002
CHANGE VESSEL TYPE (Invoicing issue) | COPT Support | Bug / Defect | Critical | 2025-01-27 | 2025-01-21 | Closed | 20250121001
Re: As per SoR Clause No. 2.1.2 Sl. No.03- Port dues exemption issue in marine Invoice. | COPT Support | Bug / Defect | Critical | 2025-01-28 | 2025-01-12 | Closed | 2025012001
Re: Delay in the transmission of the CALINV message. | COPT Support | Bug / Defect | Critical | 2025-01-21 | 2025-01-12 | Closed | 2025012101
Stuffing and storage charge invoices reg.. | COPT Support | Bug / Defect | Critical | 2025-01-27 | 2025-01-12 | Closed | 2025012002
Provision to record Anchorage details and invoice through system | COPT Support | Bug / Defect | Critical | 2025-02-06 | 2025-01-29 | Closed | 20250129001
Discount amount should be reflected in place of zero in final invoice | COPT Support | Bug / Defect | Critical | 2025-02-07 | 2025-01-06 | Closed | 20241237001
POS - Mobile App | COPT Support | Bug / Defect | Critical | 2025-02-08 | 2025-02-12 | Closed | 20250212002
feature to export each invoices in PDF format (preferred naming convention: InvoiceNo_InvoiceDate_PDAccountNo.pdf) | COPT Support | Bug / Defect | Critical | 2025-02-08 | 2025-02-17 | InProcess | 20250217001
IGM Issue- CFS Portkonnect | COPT Support | Bug / Defect | Critical | 2025-02-08 | 2025-04-07 | InProcess | 20250407001
Re: GAS AL KUWAIT II-INCOK125020037 - Portdues SGST/CGST Not applicable- | COPT Support | Bug / Defect | Critical | 2025-02-08 | 2025-03-04 | InProcess | 20250304001
Escalation of Scale of Rates of Cochin Port w.e.f. 01.05.2025 | COPT Support | Bug / Defect | Critical | 2025-02-09 | 2025-04-24 | InProcess | 20250424001
Bunkering New Requirements | COPT Support | Bug / Defect | Critical | 2025-02-10 | 2025-05-14 | InProcess | 20250514001
OTP Based Login | COPT Support | Bug / Defect | Critical | 2025-05-28 | 2025-05-14 | InProcess | 20250514002
Port clearence document issue- Select Days as 3 By default | COPT Support | Bug / Defect | Critical | 2025-05-29 | 2025-05-06 | InProcess | 20250506002
View permission for the database | COPT Support | Bug / Defect | Critical | 2025-05-30 | 2025-05-05 | InProcess | 20250505001
Request for removal of berth rate for AMBA JETTY from system. | COPT Support | Bug / Defect | Critical | 2025-05-31 | 2025-05-06 | InProcess | 20250506001
Request for Modification in Portkonnect Application - Finance Module Interface. | COPT Support | Bug / Defect | Critical | 2025-06-01 | 2025-06-17 | InProcess | 20250617001

## Status
1 | New
2 | InProcess
3 | Resolved
4 | Closed
5 | Hold

## Project
1 | COPT Support
2 | Miscellaneous Activity

## Category
1 | Bug / Defect
2 | Feature Request
3 | Technical Support
4 | Service Request - Technical
5 | Service Request - Documentation
6 | Incident
7 | Access / Permission Issue
8 | Account Issues
9 | Performance Issue
10 | UI / UX Feedback

## Priority
1 | LOW
2 | Medium
3 | Hign
4 | Critical